## PM Showcase
Teams Invites Tracker — Tech Quick View + PM Showcase
Use the left table to scan operations. Use the dropdown on the right to instantly generate a copy/paste Teams invite body.
Tech Quick View — Operations Index | [8 empty] | Copy/Paste Generator — Teams Invite Body
Event ID | Date | Start | End | Title | Location | Required | Optional | Status | Event ID | AP-2026-02-22
AP-2026-01-08 | 46030 | 0.33333 | 0.70833 | Alejandro - 3HQ Key Drop + HQ Plainview Config + PBMC Prep (1/8) | HQ - Plainview (multi-stop details in agenda) | Alejandro Perales | Ralph (3HQ) ; Khadejah Harrison ; Akbar (if he's the config owner) | Planned | Title | LIJ ORs - Cybernet + GCX Arm Deployment (Day 2 of 2)
KH-2026-01-08 | 46030 | 0.33333 | 0.70833 | Khadejah — Inventory Counts + Locations (1 Marcus + HQ) + Pallets + Arm Attach Doc (1/8) | HQ + 1 Marcus (multi-stop counts + pallets; details in agenda) | Khadejah Harrison | Rich Perez ; Bonita Outlaw | Planned | Date | 2026-02-22
IP-2026-01-12 | 46034 | 0.375 | 0.75 | iPhone/Rover — Recurring Training Block (Starts Week of 1/12) | Training window (no meeting link) | Emmanuel Sanchez; Ezekiel; Erik Guzman; Julio Mojica; Asher Ali; Valentyn Nykoliuk; Tanjim Khan; Shazaib Idrees; Cyen Heyliger; Connor Hoffman | Nayelin Monegro; Rich Perez | Planned | Time | 8:00 AM - 6:00 PM Local
MV-2026-01-11 | 46033 | 0.33333 | 0.70833 | LIJ SDF Sunday — Transport + Pack-Out (Marvin Lead) — 28 all around | Stock staging room → LIJ SDF | Marvin Tate | Rich Perez; Bonita Outlaw | Planned | Location | LIJ Main - OR Suite
PM-2026-01-19 | 46041 | 0.375 | 0.75 | Patricia — iPhone/Rover — Recurring Training Block (Starts Week of 1/21) | LHH and the Northern Westchester Area | Patricia Marrero | Rich Perez; Josh Vincent | 0 | Invite QA | Missing Status
MT-2026-01-21 | 46043 | 0.375 | 0.45833 | MEETH — Stock Delivery (Marvin Lead) | MEETH | Marvin Tate | Rich Perez; Bonita Outlaw | Planned | Teams Body (copy/paste) | (click cell below, Ctrl+A, Ctrl+C)
KH-2026-01-27 | 46049 | 0.375 | 0.625 | Glen Cove — OR/Endo Cybernet Peripherals Install (9 KB+Mouse, 9 Badge Readers, 9 Barcode Scanners) | Glen Cove Hospital — OR & Endo (Cybernet) | Khadejah Harrison; CDW Resource (TBD) | Timothy Seeberger | 0 | Purpose Continue LIJ ORs deployment/testing. FIRST ACTION: confirm PA creds still working (or re-activate if needed). Same standards: GCX arms + peripherals installed; validate badge/barcode/connectivity; trackers stay live; close out open issues from Day 1. Stops (in order) 1) 08:00 kickoff + review Day 1 exceptions 2) Confirm PA creds active + quick verification 3) Stage remaining devices/parts 4) Complete remaining ORs first 5) Re-test any problem rooms 6) Update trackers continuously + resolve/escalate exceptions 7) Consolidate disposal pile + label clearly 8) 17:30 final sweep + handoff notes To-Do (hard requirements) Zero “we’ll fix it later” devices left in service. PA creds verified before work begins. Any blocker gets an owner + next action logged before wrap. Tracker stays current throughout execution. Suggested Timeline 08:00 kickoff; 08:10 PA creds verification; 08:20 staging; 09:00 deployments rolling; 15:30 begin closeout/retests; 17:30 handoff notes; 18:00 wrap Guardrails No improvising changes; keep OR sequence disciplined; escalate access/port issues immediately; keep cabling clean and standardized; update trackers as we go so status is always current. Completion signals PA creds verified; all remaining assigned devices deployed + validated; Day 1 issues resolved or owned; tracker current; closeout notes sent.
KH-2026-01-27 | 46049 | 0.375 | 0.625 | Glen Cove — OR/Endo Cybernet Peripherals Install (9 KB+Mouse, 9 Badge Readers, 9 Barcode Scanners) | Glen Cove Hospital — OR & Endo (Cybernet) | Khadejah Harrison; CDW Resource (TBD) | Timothy Seeberger | 0
GG-2026-01-30 | 46052 | 0.375 | 0.70833 | Cybernet Deployment + iPad Go-Live Support (Senior + Shadow) | Client Site — Cybernet Go-Live | Geoff Gerber; Chris Cummings | Rich Perez | 0
AA-2026-02-07 | 46060 | 0.375 | 0.70833 | CFAM — Deployment Support (One-Day Push) | CFAM (Center for Advanced Medicine) | Asher Ali; Alejandro Pelales; Delroy Harris | Patricia Marrero | Planned
KH-2026-02-09 | 46062 | 0.45833 | 0.54167 | LIJ SDF - Satellite Dialysis Facility - Testing Oversight (Noon-1) + Possible Cat6 Relay | LIJ SDF - Satellite Dialysis Facility | Khadejah Harrison | 0 | Planned
MT-2026-02-09 | 46062 | 0.70833 | 0.83333 | Franklin Hospital (Valley Stream) - Peripheral Deployment (10 units) | Franklin Hospital - Valley Stream | Marvin Tate; Khadejah Harrison | 0 | 0
| 46062 | 0 | 0 | LIJVS — Device Integration Install/Testing (W2) | LIJ Valley Stream | Khadejah Harrison; Marvin Tate | Richard Perez; Tim Seeberger | 0
AP-2026-02-14 | 46067 | 0.33333 | 0.75 | CCMC — Cybernet Deployment + iPro + OU Config (14 units) — ONE location | CCMC | Alejandro Perales; Chris Cummings; Nicholas Valentin | Rich Perez; Tim Seeberger | 0
MT-2026-02-13 | 46066 | 0.5 | 0.66667 | CCMC — HQ → Site Delivery (14 Cybernets + Peripherals) — Marvin | HQ → CCMC | Marvin Tate | Richard Perez | 0
MT-2026-02-14 | 46067 | 0.58333 | 0.75 | CCMC — Site Disposal (Post-Deployment) — Marvin Lead | CCMC | Marvin Tate | Rich Perez; Tim Seeberger | 0
AP-2026-02-21 | 46074 | 0.33333 | 0.75 | LIJ ORs - Cybernet + GCX Arm Deployment (Day 1 of 2) | LIJ Main - OR Suite | Alejandro Perales; Patricia Marrero; Valentyn Nykoliuk; Marvin Tate | Rich Perez; Tim Seeberger | 0
AP-2026-02-22 | 46075 | 0.33333 | 0.75 | LIJ ORs - Cybernet + GCX Arm Deployment (Day 2 of 2) | LIJ Main - OR Suite | Alejandro Perales; Chris Cummings; Patricia Marrero; Delroy Harris; Valentyn Nykoliuk | Rich Perez; Tim Seeberger | 0
DD-2026-02-26 | 46079 | 0.375 | 0.70833 | LIJ - Deployment Kit Delivery + Staging (Day 1 of 2) | LIJ Main - Procedural Areas + Annex | Deployment Delivery; Marvin Tate; Alejandro Perales | Rich Perez; Tim Seeberger | 0
DD-2026-02-27 | 46080 | 0.375 | 0.70833 | LIJ - Deployment Kit Delivery + Staging (Day 2 of 2) | LIJ Main - Procedural Areas + Annex | Deployment Delivery; Marvin Tate; Alejandro Perales | Rich Perez; Tim Seeberger | 0
AP-2026-02-28 | 46081 | 0.33333 | 0.75 | LIJ ORs - Cybernet + GCX Arm Deployment (Day 1 of 2) | LIJ Main - Procedural Areas | Alejandro Perales; Patricia Marrero; Valentyn Nykoliuk; Marvin Tate | Rich Perez; Tim Seeberger | 0
AP-2026-03-01 | 46082 | 0.33333 | 0.75 | LIJ ORs - Cybernet + GCX Arm Deployment (Day 2 of 2) | LIJ Main - Annex Area | Alejandro Perales; Chris Cummings; Patricia Marrero; Delroy Harris; Valentyn Nykoliuk | Rich Perez; Tim Seeberger | 0
NC-2026-03-02 | 46083 | 0.4375 | 0.625 | LIJ SDF - Neuron Capsule Variable Testing | LIJ SDF - Satellite Dialysis Facility | Neuron Capsules; LIJ SDF Tech | Jay Hernandez; Rich Perez | 0
PM-2026-02-24 | 46077 | 0.33333 | 0.70833 | LIJ - iPhones Team Coverage (Patricia Marrero onsite) | LIJ | Patricia Marrero | Nicholas Valentin (remote); Jay Hernandez | 0
CH-2026-02-25 | 46078 | 0.33333 | 0.70833 | LIJ - iPhones Team Coverage (Cyen Heyliger onsite) | LIJ | Cyen Heyliger | Jay Hernandez | 0
PM-2026-02-26 | 46079 | 0.33333 | 0.70833 | LIJ - iPhones Team Coverage (Patricia Marrero onsite) | LIJ | Patricia Marrero | Jay Hernandez | 0
CH-2026-02-27 | 46080 | 0.33333 | 0.70833 | LIJ - iPhones Team Coverage (Cyen Heyliger onsite) | LIJ | Cyen Heyliger | Jay Hernandez | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PM Showcase — Evidence Log (add wins as they happen)
Quick Stats | 26 |  |  | Total Operations (count) |  | How to use this tab: 1) Techs: use the left index table to find your operation; on the right, pick the Event ID to get a ready-to-paste Teams body. 2) PM brag file: after each operation, add one row in the Evidence Log. Keep it factual: what changed, proof, impact. Tip: If you add attachments/screenshots, paste the file name or SharePoint link in 'Evidence'.
Done | 0 |  |  | Ops marked Done
Blocked | 0 |  |  | Ops blocked (needs help)
Date | Event ID | What I led / changed | Evidence (link, note, screenshot ref) | Impact (time, risk, quality) | Next improvement
2026-01-29 | GG-2026-01-30 | Bugfix: Teams Invite Body returned 'Planned' due to Invite Builder col R (Body) being overwritten/missing formula. Restored Body formula and documented guardrail. | Screenshot: PM Showcase Teams Body cell displayed only 'Planned' despite populated Invite Builder fields. | Prevents blank/incorrect invites; reduces rework and missed stock details before go-live days. | Add guardrail: flag rows where Body is blank or equals a Status picklist value (Planned/In Progress/Blocked/Done). Consider protecting column R.
2026-01-29 | SYSTEM | Added web-safe guardrails: Row QA column, dropdown validations, conditional formatting, PM Showcase QA readout, and sheet protection to prevent formula overwrites. | See 'System Notes' tab; Invite Builder col V (Row QA) + named ranges (ShowAsList/StatusList/ReminderMinutesList/TimeZoneList). | Catches 'Body overwritten' before copy/paste, reduces rework, keeps invites reliable under Web Excel constraints.

## Invite Builder
Event ID | Title | Date | Start Time | End Time | Time Zone | Required Attendees | Optional Attendees | Location | Show As | Reminder (min) | Purpose | Stops (in order) | Hard Requirements | Suggested Timeline | Guardrails | Completion Signals | Body (Teams paste) | Checkpoint Log (actuals) | Status | Last Updated | Row QA (auto)
AP-2026-01-08 | Alejandro - 3HQ Key Drop + HQ Plainview Config + PBMC Prep (1/8) | 2026-01-08 | 8:00 | 17:00 | Local | Alejandro Perales | Ralph (3HQ) ; Khadejah Harrison ; Akbar (if he's the config owner) | HQ - Plainview (multi-stop details in agenda) | Busy | 30 | Return universal key; configure and stage devices at HQ Plainview; prep for PBMC deployment; align counts with Khadejah. | 1) 3HQ - Key drop with Ralph 2) HQ - Plainview - Device configuration + staging 3) PBMC - Deployment prep / readiness | - Contact Ralph first thing AM to coordinate key handoff. - Drop off universal key to Ralph at 3HQ and confirm receipt. - Head to HQ Plainview ASAP after key drop. - Configure devices at HQ. - Stage/pack for PBMC deployment. - Sync with Khadejah on counts before deployment. | - 8:00-8:15 Call/text Ralph; lock handoff details - 8:15-9:00 3HQ key drop -> confirm receipt - 9:00-1:00 HQ Plainview: configure devices + verification checks - 1:00-2:00 Staging/packout for PBMC - 2:00-2:15 Sync w/ Khadejah: counts + plan - 2:15+ Travel/prepare for PBMC window | - Do not accept extra add-ons without approval; log and escalate. - If Tim is involved, confirm requirements in advance. | - Key returned to Ralph + time - HQ config complete + device count - PBMC staging complete + blockers - Counts aligned with Khadejah + final count | Purpose Return universal key; configure and stage devices at HQ Plainview; prep for PBMC deployment; align counts with Khadejah. Stops (in order) 1) 3HQ - Key drop with Ralph 2) HQ - Plainview - Device configuration + staging 3) PBMC - Deployment prep / readiness To-Do (hard requirements) - Contact Ralph first thing AM to coordinate key handoff. - Drop off universal key to Ralph at 3HQ and confirm receipt. - Head to HQ Plainview ASAP after key drop. - Configure devices at HQ. - Stage/pack for PBMC deployment. - Sync with Khadejah on counts before deployment. Suggested Timeline - 8:00-8:15 Call/text Ralph; lock handoff details - 8:15-9:00 3HQ key drop -> confirm receipt - 9:00-1:00 HQ Plainview: configure devices + verification checks - 1:00-2:00 Staging/packout for PBMC - 2:00-2:15 Sync w/ Khadejah: counts + plan - 2:15+ Travel/prepare for PBMC window Guardrails - Do not accept extra add-ons without approval; log and escalate. - If Tim is involved, confirm requirements in advance. Completion signals - Key returned to Ralph + time - HQ config complete + device count - PBMC staging complete + blockers - Counts aligned with Khadejah + final count |  | Planned | 2026-01-08 07:38 | OK
KH-2026-01-08 | Khadejah — Inventory Counts + Locations (1 Marcus + HQ) + Pallets + Arm Attach Doc (1/8) | 2026-01-08 | 8:00 | 17:00 | Local | Khadejah Harrison | Rich Perez ; Bonita Outlaw | HQ + 1 Marcus (multi-stop counts + pallets; details in agenda) | Busy | 30 | Establish reliable counts + exact locations for Neuron deployment stock across HQ and 1 Marcus (including pallets); consolidate into a single master counts interface; produce shortages/blockers + runway for upcoming sites; document the arm→Neuron attach process for reuse. | 1) HQ - Sweep all staging areas + pallets; log counts + exact locations 2) 1 Marcus - Sweep stock; log counts + exact locations 3) Update Inventory Master - consolidate counts; tag conflicts; timestamp 4) Arm→Neuron attach - capture steps (photos/video) + notes 5) Send EOD summary (totals, shortages, runway, next steps) | - Record COUNT + EXACT LOCATION for each line item touched (no vague 'HQ'). - Use location format: [SITE] - [AREA] - [SUBAREA]. - Prioritize Neuron units + GCX arms first; then DIMs/adapters/KBM. - Tag pallets with a PalletID (P-001, P-002...) and record their contents. - No guessing: if a count conflicts, mark CONFLICT and note why. - Keep everything in the master tracker (no side spreadsheets). | - 8:00-10:30 HQ sweep (zones + pallets) + initial totals - 10:30-12:30 1 Marcus sweep + totals - 12:30-1:30 Update Inventory Master + reconcile conflicts - 1:30-2:15 Arm→Neuron attach documentation (clean angles) - 2:15-2:30 Send summary to Rich (HQ vs 1 Marcus totals + blockers + runway) | - Don’t move stock without updating location in the master. - If something is missing/damaged/unknown, log it immediately and flag it. - Keep photos clear; avoid capturing screens/labels not needed. - If time runs short, finish Neurons + arms + pallet manifest first. | - Master counts updated with HQ vs 1 Marcus totals + exact locations. - Pallets tagged + recorded (at least Neurons + arms per pallet). - Shortages/blockers list captured. - Arm→Neuron attach steps recorded + shared. - EOD summary sent. | Purpose Establish reliable counts + exact locations for Neuron deployment stock across HQ and 1 Marcus (including pallets); consolidate into a single master counts interface; produce shortages/blockers + runway for upcoming sites; document the arm→Neuron attach process for reuse. Stops (in order) 1) HQ - Sweep all staging areas + pallets; log counts + exact locations 2) 1 Marcus - Sweep stock; log counts + exact locations 3) Update Inventory Master - consolidate counts; tag conflicts; timestamp 4) Arm→Neuron attach - capture steps (photos/video) + notes 5) Send EOD summary (totals, shortages, runway, next steps) To-Do (hard requirements) - Record COUNT + EXACT LOCATION for each line item touched (no vague 'HQ'). - Use location format: [SITE] - [AREA] - [SUBAREA]. - Prioritize Neuron units + GCX arms first; then DIMs/adapters/KBM. - Tag pallets with a PalletID (P-001, P-002...) and record their contents. - No guessing: if a count conflicts, mark CONFLICT and note why. - Keep everything in the master tracker (no side spreadsheets). Suggested Timeline - 8:00-10:30 HQ sweep (zones + pallets) + initial totals - 10:30-12:30 1 Marcus sweep + totals - 12:30-1:30 Update Inventory Master + reconcile conflicts - 1:30-2:15 Arm→Neuron attach documentation (clean angles) - 2:15-2:30 Send summary to Rich (HQ vs 1 Marcus totals + blockers + runway) Guardrails - Don’t move stock without updating location in the master. - If something is missing/damaged/unknown, log it immediately and flag it. - Keep photos clear; avoid capturing screens/labels not needed. - If time runs short, finish Neurons + arms + pallet manifest first. Completion signals - Master counts updated with HQ vs 1 Marcus totals + exact locations. - Pallets tagged + recorded (at least Neurons + arms per pallet). - Shortages/blockers list captured. - Arm→Neuron attach steps recorded + shared. - EOD summary sent. |  | Planned | 2026-01-08 07:56 | OK
IP-2026-01-12 | iPhone/Rover — Recurring Training Block (Starts Week of 1/12) | 2026-01-12 | 9:00 | 18:00 | Local | Emmanuel Sanchez; Ezekiel; Erik Guzman; Julio Mojica; Asher Ali; Valentyn Nykoliuk; Tanjim Khan; Shazaib Idrees; Cyen Heyliger; Connor Hoffman | Nayelin Monegro; Rich Perez | Training window (no meeting link) | Busy | 30 | Recurring iPhone/Rover shadow training window + Training Log updates; identify knowledge gaps and drive follow-up shadowing. | 1) Trainee sends mentor availability + site + constraints 2) Mentor confirms capacity + schedules shadow block(s) 3) Shadow block happens 4) Same-day Training Log update (coverage + gaps + next topic) 5) Repeat as needed until well-rounded | - Training Log is the source of truth - Same-day log updates after each shadow block - Capture knowledge gaps + next recommended topic - Escalate access/permissions blockers; don’t improvise | Week of 1/12: schedule the first shadow blocks early in the week Ongoing: repeat shadow blocks as needed; Training Log updated same day | - No surprise reassignments without notifying the group - No side chats as the “real plan” - If blocked by access/permissions, escalate immediately | - First shadow block scheduled per trainee - Training Log updated after each shadow block - Knowledge gaps logged + follow-up topics assigned | iPhone/Rover Shadow Training — Recurring Block (Starts Week of 1/12) This is a training window, not a meeting. Use this block to schedule and complete shadow sessions. No one needs to join. What this is: A recurring training window for iPhone/Rover shadowing + skill-building. Each trainee completes at least 1–2 shadow blocks to start, then continues as needed. Knowledge gaps get logged and tracked. Mentors: • Emmanuel Sanchez (Lenox Hill) • Erik Guzman (PBMC) • Ezekiel (Staten Island N&S) Trainees: • Julio Mojica • Asher Ali • Valentyn Nykoliuk • Tanjim Khan • Shazaib Idrees • Cyen Heyliger • Connor Hoffman TRAINEES — DO THIS Send your mentor: • Two time windows next week you can shadow (and more as needed) • Your main site • Any constraints (access issues, hard stop time, etc.) After each shadow block: • Update the Training Log the same day (what was covered + knowledge gaps + next topic) MENTORS — DO THIS • Tell me how many trainees you can actively support at a time • Coordinate shadow blocks with those trainees • Update the Training Log with: Trainee / Mentor / Date-Time / Site / What was covered / Knowledge gaps & blockers / Next recommended topic RULE Training Log is the source of truth. No side chats as the “real plan.” |  | Planned | 2026-01-10 07:34 | OK
MV-2026-01-11 | LIJ SDF Sunday — Transport + Pack-Out (Marvin Lead) — 28 all around | 2026-01-11 | 8:00 | 17:00 | Local | Marvin Tate | Rich Perez; Bonita Outlaw | Stock staging room → LIJ SDF | Busy | 30 | Move the correct stock to LIJ SDF for Sunday’s work; keep staging controlled; pack out everything we bring in so LIJ SDF returns to pre-arrival condition. Key rule: 28 all around (28 capsules + 28 of each required cable/cord type). | 1) Staging room (pull / count / organize) 2) Load vehicle 3) LIJ SDF (deliver staged stock) 4) End-of-day pack-out + close-out proof | • Confirm exact item list for Sunday (capsules + cables/cords + accessories) • Pull & stage: 28 capsules (7 boxes × 4) • Pull & stage: 28 Ethernet cables • Pull & stage: 28 power cords • Pull & stage: 28 of any other required cable/cord type (default to 28 unless PM specifies otherwise) • HQ path: if mounts/arms are delivered separately, pack out all packaging + unused materials • Keep stock orderly: stack by category; labels facing out; pallet jack accessible • Keep walking/loading path clear (no loose cables/garbage) • Take quick photo of staged load before moving out • Load securely (heavy bottom; protect fragile; prevent shifting) • Pack-out rules: remove all packaging created + all unused stock; keep device/capsule shipping boxes • Damaged/questionable items: bag/tag + bring back (no trashing devices/cables) • Final walk-through: floors clear; carts/pallets out; nothing left behind | Before move: • Stage by category, count to 28, photo the staged load • Load + secure At site / end-of-day: • Pack out all packaging + unused stock • Take 2 close-out photos: (1) empty staging footprint at LIJ SDF, (2) load-out/packed carts ready to leave • Note any exceptions + who approved | “Disposal” = pack out everything we bring in so LIJ SDF is as it was before we arrived. Trash/packaging only. Never devices/cables. Keep device/capsule shipping boxes. Do not leave extra stock behind unless explicitly approved; document approvals. | • 28-count confirmed for capsules + each cable/cord type • Staged-load photo captured • Site packed out (no trash/packaging left) + 2 close-out photos taken • Any exceptions documented with approver | Purpose Move the correct stock to LIJ SDF for Sunday’s work; keep staging controlled; pack out everything we bring in so LIJ SDF returns to pre-arrival condition. Key rule: 28 all around (28 capsules + 28 of each required cable/cord type). Stops (in order) 1) Staging room (pull / count / organize) 2) Load vehicle 3) LIJ SDF (deliver staged stock) 4) End-of-day pack-out + close-out proof To-Do (hard requirements) • Confirm exact item list for Sunday (capsules + cables/cords + accessories) • Pull & stage: 28 capsules (7 boxes × 4) • Pull & stage: 28 Ethernet cables • Pull & stage: 28 power cords • Pull & stage: 28 of any other required cable/cord type (default to 28 unless PM specifies otherwise) • HQ path: if mounts/arms are delivered separately, pack out all packaging + unused materials • Keep stock orderly: stack by category; labels facing out; pallet jack accessible • Keep walking/loading path clear (no loose cables/garbage) • Take quick photo of staged load before moving out • Load securely (heavy bottom; protect fragile; prevent shifting) • Pack-out rules: remove all packaging created + all unused stock; keep device/capsule shipping boxes • Damaged/questionable items: bag/tag + bring back (no trashing devices/cables) • Final walk-through: floors clear; carts/pallets out; nothing left behind Suggested Timeline Before move: • Stage by category, count to 28, photo the staged load • Load + secure At site / end-of-day: • Pack out all packaging + unused stock • Take 2 close-out photos: (1) empty staging footprint at LIJ SDF, (2) load-out/packed carts ready to leave • Note any exceptions + who approved Guardrails “Disposal” = pack out everything we bring in so LIJ SDF is as it was before we arrived. Trash/packaging only. Never devices/cables. Keep device/capsule shipping boxes. Do not leave extra stock behind unless explicitly approved; document approvals. Completion signals • 28-count confirmed for capsules + each cable/cord type • Staged-load photo captured • Site packed out (no trash/packaging left) + 2 close-out photos taken • Any exceptions documented with approver |  | Planned | 2026-01-10 08:50 | OK
PM-2026-01-19 | Patricia — iPhone/Rover — Recurring Training Block (Starts Week of 1/21) | 2026-01-19 | 9:00 | 18:00 | Local | Patricia Marrero | Rich Perez; Josh Vincent | LHH and the Northern Westchester Area |  |  | • Train on iPhones and Mobile Devices • Avoid conflicts with other projects, particularly TOW • Increase the Volume and Integrity of Coverage in the Westchester area | • LHH and the Northern Westchester Area • Clarify with Mentors | • Correspond with Mentors • Train under mentors • Establish sites to cover with Eman, Connor, and Clifford | Recurring until Friday, Feb 6 | • No conflicts with DSE and TOW • Avoid TOW and DSE conflicts | • No conflicts with DSE and TOW • Correspondence with Mentors in Effect • Training log updated with updated knowledge gaps | Purpose • Train on iPhones and Mobile Devices • Avoid conflicts with other projects, particularly TOW • Increase the Volume and Integrity of Coverage in the Westchester area Stops (in order) • LHH and the Northern Westchester Area • Clarify with Mentors To-Do (hard requirements) • Correspond with Mentors • Train under mentors • Establish sites to cover with Eman, Connor, and Clifford Suggested Timeline Recurring until Friday, Feb 6 Guardrails • No conflicts with DSE and TOW • Avoid TOW and DSE conflicts Completion signals • No conflicts with DSE and TOW • Correspondence with Mentors in Effect • Training log updated with updated knowledge gaps |  |  |  | Missing Status
MT-2026-01-21 | MEETH — Stock Delivery (Marvin Lead) | 2026-01-21 | 9:00 | 11:00 | Local | Marvin Tate | Rich Perez; Bonita Outlaw | MEETH | Busy | 30 | Deliver critical MEETH stock (QTY 2 each) and confirm clean handoff so the site can proceed without delays. | 1) HQ stock room / staging (pull + verify) 2) Load vehicle (secure) 3) MEETH (deliver + handoff) 4) Return / close-out (update counts + note exceptions) | ☐ Pick up required items directly from Geoff Gerber ☐ Verify all five SKUs are present (2 each) ☐ Keep items grouped and labeled for MEETH ☐ Photo staged items before loading ☐ Coordinate onsite handoff; record recipient name/area ☐ Photo delivery/handoff confirmation ☐ If missing/damaged: bag/tag + escalate immediately • Pull + verify the following stock (QTY 2 each): • B1-CPAT-DIM-14 — 2 • DIM — 2 • B1-CFU — 2 • SPEC999015 — 2 • GE-ADAPTOR — 2 • Keep items grouped + labeled for MEETH (no mixed piles) • Take a quick photo of the staged items before loading (proof + reference) • Coordinate onsite handoff (recipient name/area) and confirm delivery complete • If anything is missing/damaged: bag/tag and escalate immediately (do not substitute silently) | Before departure: pull + verify + photo. At MEETH: handoff + confirm recipient. After: update tracker / notes with any exceptions. | This is a controlled delivery. No improvising part substitutions without approval. Keep packaging tidy; prevent damage in transit. | All five SKUs delivered (2 each), recipient confirmed, and staging/delivery photo captured. Exceptions logged if any. | Purpose Deliver critical MEETH stock (QTY 2 each) and confirm clean handoff so the site can proceed without delays. Stops (in order) 1) HQ stock room / staging (pull + verify) 2) Load vehicle (secure) 3) MEETH (deliver + handoff) 4) Return / close-out (update counts + note exceptions) To-Do (hard requirements) ☐ Pick up required items directly from Geoff Gerber ☐ Verify all five SKUs are present (2 each) ☐ Keep items grouped and labeled for MEETH ☐ Photo staged items before loading ☐ Coordinate onsite handoff; record recipient name/area ☐ Photo delivery/handoff confirmation ☐ If missing/damaged: bag/tag + escalate immediately • Pull + verify the following stock (QTY 2 each): • B1-CPAT-DIM-14 — 2 • DIM — 2 • B1-CFU — 2 • SPEC999015 — 2 • GE-ADAPTOR — 2 • Keep items grouped + labeled for MEETH (no mixed piles) • Take a quick photo of the staged items before loading (proof + reference) • Coordinate onsite handoff (recipient name/area) and confirm delivery complete • If anything is missing/damaged: bag/tag and escalate immediately (do not substitute silently) Suggested Timeline Before departure: pull + verify + photo. At MEETH: handoff + confirm recipient. After: update tracker / notes with any exceptions. Guardrails This is a controlled delivery. No improvising part substitutions without approval. Keep packaging tidy; prevent damage in transit. Completion signals All five SKUs delivered (2 each), recipient confirmed, and staging/delivery photo captured. Exceptions logged if any. |  | Planned | 2026-01-20 12:00 | OK
KH-2026-01-27 | Glen Cove — OR/Endo Cybernet Peripherals Install (9 KB+Mouse, 9 Badge Readers, 9 Barcode Scanners) | 2026-01-27 | 9:00 | 15:00 | Local | Khadejah Harrison; CDW Resource (TBD) | Timothy Seeberger | Glen Cove Hospital — OR & Endo (Cybernet) | Busy | 30 | Install and validate 9 wired keyboard/mouse sets, 9 badge access readers, and 9 barcode scanners; connect all peripherals to the Cybernet in OR and Endo. | 1) 3HQ (as needed): confirm delivery/availability of 9 cables for Glen Cove ¦ 2) Glen Cove — OR: install/connect/test peripherals on Cybernet ¦ 3) Glen Cove — Endo: install/connect/test peripherals on Cybernet ¦ 4) Close-out: photos (no PHI) + confirm counts + send completion note | Verify inventory (9 KB+Mouse, 9 Badge Readers, 9 Barcode Scanners; plus 9 cables if applicable) ¦ Install + connect to correct Cybernet(s) in OR & Endo ¦ Test: keyboard/mouse input, badge read, barcode scan ¦ Escalate blockers immediately (ports/driver/access) ¦ No silent substitutions | Before: confirm stock/cables at 3HQ if needed ¦ Onsite: OR first, then Endo ¦ End: confirm with site POC + send completion update | No PHI in photos ¦ Keep cabling tidy/secured ¦ Same-day escalation on blockers; coordinate access with site IT as needed | All 27 peripherals installed + tested in OR/Endo ¦ Exceptions logged with owner/next step ¦ Completion update sent | Purpose Install and validate 9 wired keyboard/mouse sets, 9 badge access readers, and 9 barcode scanners; connect all peripherals to the Cybernet in OR and Endo. Stops (in order) 1) 3HQ (as needed): confirm delivery/availability of 9 cables for Glen Cove ¦ 2) Glen Cove — OR: install/connect/test peripherals on Cybernet ¦ 3) Glen Cove — Endo: install/connect/test peripherals on Cybernet ¦ 4) Close-out: photos (no PHI) + confirm counts + send completion note To-Do (hard requirements) Verify inventory (9 KB+Mouse, 9 Badge Readers, 9 Barcode Scanners; plus 9 cables if applicable) ¦ Install + connect to correct Cybernet(s) in OR & Endo ¦ Test: keyboard/mouse input, badge read, barcode scan ¦ Escalate blockers immediately (ports/driver/access) ¦ No silent substitutions Suggested Timeline Before: confirm stock/cables at 3HQ if needed ¦ Onsite: OR first, then Endo ¦ End: confirm with site POC + send completion update Guardrails No PHI in photos ¦ Keep cabling tidy/secured ¦ Same-day escalation on blockers; coordinate access with site IT as needed Completion signals All 27 peripherals installed + tested in OR/Endo ¦ Exceptions logged with owner/next step ¦ Completion update sent |  |  |  | Missing Status
KH-2026-01-27 | Glen Cove — OR/Endo Cybernet Peripherals Install (9 KB+Mouse, 9 Badge Readers, 9 Barcode Scanners) | 2026-01-27 | 9:00 | 15:00 | Local | Khadejah Harrison; CDW Resource (TBD) | Timothy Seeberger | Glen Cove Hospital — OR & Endo (Cybernet) | Busy | 30 | Install and validate 9 wired keyboard/mouse sets, 9 badge access readers, and 9 barcode scanners; connect all peripherals to the Cybernet in OR and Endo. | 1) 3HQ (as needed): confirm delivery/availability of 9 cables for Glen Cove ¦ 2) Glen Cove — OR: install/connect/test peripherals on Cybernet ¦ 3) Glen Cove — Endo: install/connect/test peripherals on Cybernet ¦ 4) Close-out: photos (no PHI) + confirm counts + send completion note | Verify inventory (9 KB+Mouse, 9 Badge Readers, 9 Barcode Scanners; plus 9 cables if applicable) ¦ Install + connect to correct Cybernet(s) in OR & Endo ¦ Test: keyboard/mouse input, badge read, barcode scan ¦ Escalate blockers immediately (ports/driver/access) ¦ No silent substitutions | Before: confirm stock/cables at 3HQ if needed ¦ Onsite: OR first, then Endo ¦ End: confirm with site POC + send completion update | No PHI in photos ¦ Keep cabling tidy/secured ¦ Same-day escalation on blockers; coordinate access with site IT as needed | All 27 peripherals installed + tested in OR/Endo ¦ Exceptions logged with owner/next step ¦ Completion update sent | Purpose Install and validate 9 wired keyboard/mouse sets, 9 badge access readers, and 9 barcode scanners; connect all peripherals to the Cybernet in OR and Endo. Stops (in order) 1) 3HQ (as needed): confirm delivery/availability of 9 cables for Glen Cove ¦ 2) Glen Cove — OR: install/connect/test peripherals on Cybernet ¦ 3) Glen Cove — Endo: install/connect/test peripherals on Cybernet ¦ 4) Close-out: photos (no PHI) + confirm counts + send completion note To-Do (hard requirements) Verify inventory (9 KB+Mouse, 9 Badge Readers, 9 Barcode Scanners; plus 9 cables if applicable) ¦ Install + connect to correct Cybernet(s) in OR & Endo ¦ Test: keyboard/mouse input, badge read, barcode scan ¦ Escalate blockers immediately (ports/driver/access) ¦ No silent substitutions Suggested Timeline Before: confirm stock/cables at 3HQ if needed ¦ Onsite: OR first, then Endo ¦ End: confirm with site POC + send completion update Guardrails No PHI in photos ¦ Keep cabling tidy/secured ¦ Same-day escalation on blockers; coordinate access with site IT as needed Completion signals All 27 peripherals installed + tested in OR/Endo ¦ Exceptions logged with owner/next step ¦ Completion update sent | Planned |  | 2026-01-25 12:00 | Missing Status
GG-2026-01-30 | Cybernet Deployment + iPad Go-Live Support (Senior + Shadow) | 2026-01-30 | 9:00 | 17:00 | Local | Geoff Gerber; Chris Cummings | Rich Perez | Client Site — Cybernet Go-Live | Busy | 30 | Deploy Cybernets and provide all-day go-live support. Client paid for 1 senior tech (Geoff) with 1 shadow tech (Chris Cummings). Stock: Geoff to have 2 Cybernets. iPad: already delivered last Friday. | 1) HQ/warehouse (if needed): pull/verify 2 Cybernets for Geoff (asset tags/serials recorded). 2) Client site: confirm iPad onsite, deploy Cybernets, provide go-live support all day. 3) End-of-day: document issues + send completion note. | • Geoff must have 2 Cybernets ready for deployment • iPad is already onsite (verify on arrival) • Chris shadows Geoff the full day • Log go-live issues + escalate blockers immediately | AM: arrival + verify iPad + deploy Cybernets. Midday: stabilize + support go-live flow. PM: mop-up issues + handoff + send summary. | No PHI in notes/photos. No silent substitutions. Escalate blockers same-day and document owners/next steps. | 2 Cybernets deployed/validated. Go-live support delivered all day. Issues/next steps logged. Completion update sent. | Purpose Deploy Cybernets and provide all-day go-live support. Client paid for 1 senior tech (Geoff) with 1 shadow tech (Chris Cummings). Stock: Geoff to have 2 Cybernets. iPad: already delivered last Friday. Stops (in order) 1) HQ/warehouse (if needed): pull/verify 2 Cybernets for Geoff (asset tags/serials recorded). 2) Client site: confirm iPad onsite, deploy Cybernets, provide go-live support all day. 3) End-of-day: document issues + send completion note. To-Do (hard requirements) • Geoff must have 2 Cybernets ready for deployment • iPad is already onsite (verify on arrival) • Chris shadows Geoff the full day • Log go-live issues + escalate blockers immediately Suggested Timeline AM: arrival + verify iPad + deploy Cybernets. Midday: stabilize + support go-live flow. PM: mop-up issues + handoff + send summary. Guardrails No PHI in notes/photos. No silent substitutions. Escalate blockers same-day and document owners/next steps. Completion signals 2 Cybernets deployed/validated. Go-live support delivered all day. Issues/next steps logged. Completion update sent. |  |  | 2026-01-29 12:00 | Missing Status
AA-2026-02-07 | CFAM — Deployment Support (One-Day Push) | 2026-02-07 | 9:00 | 17:00 | Local | Asher Ali; Alejandro Pelales; Delroy Harris | Patricia Marrero | CFAM (Center for Advanced Medicine) | Busy | 30 | Extra deployment coverage at CFAM to complete the work in one day (9–5). Focus: throughput, troubleshooting, and clean handoff. | 1) 09:00 kickoff + scope check; 2) Stage devices + verify ready state; 3) Deploy + validate as you go; 4) Triage issues + escalate blockers fast; 5) 16:30 final sweep + handoff notes; 6) 17:00 exit | Full 9–5 coverage; keep tracker updates current; call out blockers early; document exceptions; leave the site clean. | 09:00 kickoff; 09:15 staging; 10:00 deployments rolling; 15:30 start final sweep; 16:30 handoff notes; 17:00 wrap | No improvising scope changes; escalate access/permissions immediately; protect clinical areas; keep footprint minimal; avoid bottlenecks by working in parallel. | All assigned devices deployed + validated; exceptions logged with owner/next step; handoff notes sent same day. | Purpose Extra deployment coverage at CFAM to complete the work in one day (9–5). Focus: throughput, troubleshooting, and clean handoff. Stops (in order) 1) 09:00 kickoff + scope check; 2) Stage devices + verify ready state; 3) Deploy + validate as you go; 4) Triage issues + escalate blockers fast; 5) 16:30 final sweep + handoff notes; 6) 17:00 exit To-Do (hard requirements) Full 9–5 coverage; keep tracker updates current; call out blockers early; document exceptions; leave the site clean. Suggested Timeline 09:00 kickoff; 09:15 staging; 10:00 deployments rolling; 15:30 start final sweep; 16:30 handoff notes; 17:00 wrap Guardrails No improvising scope changes; escalate access/permissions immediately; protect clinical areas; keep footprint minimal; avoid bottlenecks by working in parallel. Completion signals All assigned devices deployed + validated; exceptions logged with owner/next step; handoff notes sent same day. |  | Planned | 2026-01-31 | OK
KH-2026-02-09 | LIJ SDF - Satellite Dialysis Facility - Testing Oversight (Noon-1) + Possible Cat6 Relay | 2026-02-09 | 11:00 | 13:00 | Local | Khadejah Harrison |  | LIJ SDF - Satellite Dialysis Facility | Busy | 30 | Oversee testing support at LIJ SDF (testing window 12:00-1:00) and capture outcomes; relay up to 25 x 25-ft Cat6 cables if requested. | 1) Check in with site POC + confirm testing station(s) ¦ 2) Observe testing (12:00-1:00) + capture pass/fail/issues ¦ 3) If requested: pull/relay 25 x 25-ft Cat6 to designated drop location ¦ 4) Send completion note (testing results + any cable relay details) | Arrive by 11:00 for setup/coordination ¦ Document testing results (what passed/failed + owner/next step) ¦ If Cat6 relay happens: verify count (25) and record destination ¦ No PHI in notes/photos ¦ Escalate blockers same-day | 11:00 arrive + scope check ¦ 12:00 testing start ¦ 12:45 pre-wrap + confirm any cable request ¦ 13:00 wrap + send update | Keep footprint minimal in clinical areas ¦ No PHI in notes/photos ¦ If asked to move cables, confirm receiver + drop location before transport ¦ Escalate access/permissions immediately | Testing observed and results captured ¦ Issues logged with owner/next step ¦ If Cat6 relay requested: count + destination documented ¦ Completion update sent | Purpose Oversee testing support at LIJ SDF (testing window 12:00-1:00) and capture outcomes; relay up to 25 x 25-ft Cat6 cables if requested. Stops (in order) 1) Check in with site POC + confirm testing station(s) ¦ 2) Observe testing (12:00-1:00) + capture pass/fail/issues ¦ 3) If requested: pull/relay 25 x 25-ft Cat6 to designated drop location ¦ 4) Send completion note (testing results + any cable relay details) To-Do (hard requirements) Arrive by 11:00 for setup/coordination ¦ Document testing results (what passed/failed + owner/next step) ¦ If Cat6 relay happens: verify count (25) and record destination ¦ No PHI in notes/photos ¦ Escalate blockers same-day Suggested Timeline 11:00 arrive + scope check ¦ 12:00 testing start ¦ 12:45 pre-wrap + confirm any cable request ¦ 13:00 wrap + send update Guardrails Keep footprint minimal in clinical areas ¦ No PHI in notes/photos ¦ If asked to move cables, confirm receiver + drop location before transport ¦ Escalate access/permissions immediately Completion signals Testing observed and results captured ¦ Issues logged with owner/next step ¦ If Cat6 relay requested: count + destination documented ¦ Completion update sent |  | Planned | 2026-02-09 | OK
MT-2026-02-09 | Franklin Hospital (Valley Stream) - Peripheral Deployment (10 units) | 2026-02-09 | 17:00 | 20:00 | Local | Marvin Tate; Khadejah Harrison |  | Franklin Hospital - Valley Stream | Busy | 30 | Deploy and validate 10 peripherals (barcode scanner(s), badge scanner(s), mouse, keyboard) at Franklin Hospital Valley Stream. | 1) Check in + confirm target stations/rooms ¦ 2) Stage peripherals + verify total count (10) ¦ 3) Install/connect + functional test each unit as you go ¦ 4) Label/asset-tag as required ¦ 5) Close-out: confirm counts + document placements/exceptions + send completion note | Verify inventory count before leaving/onsite (10 total) ¦ Test each peripheral immediately (badge read, barcode scan, keyboard/mouse input) ¦ Keep cabling tidy ¦ Log exceptions with owner/next step ¦ No silent substitutions | 17:00 kickoff + station list ¦ 17:15 staging ¦ 17:30 installs rolling ¦ 19:30 final sweep + issue triage ¦ 20:00 wrap + send update (end time may flex if needed) | No PHI in notes/photos ¦ Escalate port/driver/access blockers immediately ¦ Keep footprint minimal and area clean ¦ Avoid half-finished stations; finish and validate before moving on | 10 peripherals installed + tested ¦ Exceptions logged with owner/next step ¦ Completion update sent | Purpose Deploy and validate 10 peripherals (barcode scanner(s), badge scanner(s), mouse, keyboard) at Franklin Hospital Valley Stream. Stops (in order) 1) Check in + confirm target stations/rooms ¦ 2) Stage peripherals + verify total count (10) ¦ 3) Install/connect + functional test each unit as you go ¦ 4) Label/asset-tag as required ¦ 5) Close-out: confirm counts + document placements/exceptions + send completion note To-Do (hard requirements) Verify inventory count before leaving/onsite (10 total) ¦ Test each peripheral immediately (badge read, barcode scan, keyboard/mouse input) ¦ Keep cabling tidy ¦ Log exceptions with owner/next step ¦ No silent substitutions Suggested Timeline 17:00 kickoff + station list ¦ 17:15 staging ¦ 17:30 installs rolling ¦ 19:30 final sweep + issue triage ¦ 20:00 wrap + send update (end time may flex if needed) Guardrails No PHI in notes/photos ¦ Escalate port/driver/access blockers immediately ¦ Keep footprint minimal and area clean ¦ Avoid half-finished stations; finish and validate before moving on Completion signals 10 peripherals installed + tested ¦ Exceptions logged with owner/next step ¦ Completion update sent |  |  |  | Missing Status
| LIJVS — Device Integration Install/Testing (W2) | 2026-02-09 |  |  | Local | Khadejah Harrison; Marvin Tate | Richard Perez; Tim Seeberger | LIJ Valley Stream | Busy | 15 | Device Integration install/testing. Standard deployment kit applies. Endo MX550 requires MIB card (confirm qty). | [5 empty] | Purpose Device Integration install/testing. Standard deployment kit applies. Endo MX550 requires MIB card (confirm qty). |  |  |  | Missing Start ¦ Missing End ¦ Missing Status
AP-2026-02-14 | CCMC — Cybernet Deployment + iPro + OU Config (14 units) — ONE location | 2026-02-14 | 8:00 | 18:00 | Local | Alejandro Perales; Chris Cummings; Nicholas Valentin | Rich Perez; Tim Seeberger | CCMC | Busy | 15 | Deploy 14 Cybernets at CCMC (ONE location) with GCX arms + peripherals; complete iPro installs and OU/group alignment. | 1) Stage 14 Cybernets + peripherals + GCX arms 2) Confirm ONE location with site POC 3) Remove/replace legacy PCs as needed 4) Install GCX arms + mount Cybernets 5) Install iPro 6) Apply OU/group alignment 7) Validate badge + barcode + connectivity 8) Label/cable-manage 9) Clean-up + prep disposal pile | • 14 Anesthesia Machines Upgraded with New Cybernets & Peripherals • 14 Anesthesia Machine Deployments Documented in the tracker • Clarify the disposal path with Tim (1 Marcus until they give us permission to discard or allocate somewhere) |  | • Activate PA Creds ahead of deployment | Devices Documented and Tested | Purpose Deploy 14 Cybernets at CCMC (ONE location) with GCX arms + peripherals; complete iPro installs and OU/group alignment. Stops (in order) 1) Stage 14 Cybernets + peripherals + GCX arms 2) Confirm ONE location with site POC 3) Remove/replace legacy PCs as needed 4) Install GCX arms + mount Cybernets 5) Install iPro 6) Apply OU/group alignment 7) Validate badge + barcode + connectivity 8) Label/cable-manage 9) Clean-up + prep disposal pile To-Do (hard requirements) • 14 Anesthesia Machines Upgraded with New Cybernets & Peripherals • 14 Anesthesia Machine Deployments Documented in the tracker • Clarify the disposal path with Tim (1 Marcus until they give us permission to discard or allocate somewhere) Guardrails • Activate PA Creds ahead of deployment Completion signals Devices Documented and Tested |  |  |  | Missing Status
MT-2026-02-13 | CCMC — HQ → Site Delivery (14 Cybernets + Peripherals) — Marvin | 2026-02-13 | 12:00 | 16:00 | Local | Marvin Tate | Richard Perez | HQ → CCMC | Busy | 15 | Deliver 13 Cybernets + peripherals from HQ to CCMC. Confirm staging location and handoff POC on arrival. |  | Confirm vehicle/transport; confirm receiving contact; confirm inventory count (14). |  |  |  | Purpose Deliver 13 Cybernets + peripherals from HQ to CCMC. Confirm staging location and handoff POC on arrival. To-Do (hard requirements) Confirm vehicle/transport; confirm receiving contact; confirm inventory count (14). |  |  |  | Missing Status
MT-2026-02-14 | CCMC — Site Disposal (Post-Deployment) — Marvin Lead | 2026-02-14 | 14:00 | 18:00 | Local | Marvin Tate | Rich Perez; Tim Seeberger | CCMC | Busy | 15 | Dispose of all deployment-related materials at CCMC: existing PCs, existing PC arms, and all boxes/trash from newly deployed equipment. | 1) Identify disposal area + confirm with site POC 2) Remove existing PCs 3) Remove existing arms 4) Consolidate all boxes/trash from new gear 5) Dispose per site process 6) Confirm area left clean + take quick photo evidence (optional) | • All Extras and Scraps removed from CCMC • Clarify where to move the stock with Tim (1 Marcus until they give us permission to discard or allocate somewhere) |  | • Activate PA Creds ahead of deployment | Photograph Clean Deployment Areas | Purpose Dispose of all deployment-related materials at CCMC: existing PCs, existing PC arms, and all boxes/trash from newly deployed equipment. Stops (in order) 1) Identify disposal area + confirm with site POC 2) Remove existing PCs 3) Remove existing arms 4) Consolidate all boxes/trash from new gear 5) Dispose per site process 6) Confirm area left clean + take quick photo evidence (optional) To-Do (hard requirements) • All Extras and Scraps removed from CCMC • Clarify where to move the stock with Tim (1 Marcus until they give us permission to discard or allocate somewhere) Guardrails • Activate PA Creds ahead of deployment Completion signals Photograph Clean Deployment Areas |  |  |  | Missing Status
AP-2026-02-21 | LIJ ORs - Cybernet + GCX Arm Deployment (Day 1 of 2) | 2026-02-21 | 8:00 | 18:00 | Local | Alejandro Perales; Patricia Marrero; Valentyn Nykoliuk; Marvin Tate | Rich Perez; Tim Seeberger | LIJ Main - OR Suite | Busy | 15 | Deploy/validate LIJ ORs (weekend block; 29 devices total across 2 days). FIRST ACTION: activate PA creds for all techs before deployments. Install Cybernet + GCX arms + peripherals (mouse, keyboard, badge reader, barcode scanner). Update trackers live as we go; log exceptions in real time. | 1) 08:00 kickoff + scope confirmation 2) PA creds activation (everyone) + quick verification 3) Stage carts/devices + verify ready state 4) ORs first: deploy + mount + cable-manage 5) Validate badge/barcode/connectivity per device 6) Update trackers continuously + log exceptions + owners 7) 17:30 final sweep + handoff notes | Bring standard baseline stock: disposal supplies, cabling/labeling, Cybernets, keyboard/mouse, badge reader test, barcode scanner test, 25-ft Cat6, breakaway adapter, GCX arm parts; PA creds must be activated/working before deployment starts; tracker access confirmed. | 08:00 kickoff; 08:10 PA creds activation; 08:20 staging; 09:00 deployments rolling; 16:30 start final sweep; 17:30 handoff notes; 18:00 wrap | No scope creep; protect clinical areas; minimal footprint; escalate access/permissions blockers immediately; update trackers as work is performed (not later); document every exception with owner + next step. | PA creds active for all techs; assigned devices deployed + validated; tracker reflects reality throughout the day; exceptions logged with owner/next step; same-day handoff notes sent. | Purpose Deploy/validate LIJ ORs (weekend block; 29 devices total across 2 days). FIRST ACTION: activate PA creds for all techs before deployments. Install Cybernet + GCX arms + peripherals (mouse, keyboard, badge reader, barcode scanner). Update trackers live as we go; log exceptions in real time. Stops (in order) 1) 08:00 kickoff + scope confirmation 2) PA creds activation (everyone) + quick verification 3) Stage carts/devices + verify ready state 4) ORs first: deploy + mount + cable-manage 5) Validate badge/barcode/connectivity per device 6) Update trackers continuously + log exceptions + owners 7) 17:30 final sweep + handoff notes To-Do (hard requirements) Bring standard baseline stock: disposal supplies, cabling/labeling, Cybernets, keyboard/mouse, badge reader test, barcode scanner test, 25-ft Cat6, breakaway adapter, GCX arm parts; PA creds must be activated/working before deployment starts; tracker access confirmed. Suggested Timeline 08:00 kickoff; 08:10 PA creds activation; 08:20 staging; 09:00 deployments rolling; 16:30 start final sweep; 17:30 handoff notes; 18:00 wrap Guardrails No scope creep; protect clinical areas; minimal footprint; escalate access/permissions blockers immediately; update trackers as work is performed (not later); document every exception with owner + next step. Completion signals PA creds active for all techs; assigned devices deployed + validated; tracker reflects reality throughout the day; exceptions logged with owner/next step; same-day handoff notes sent. |  |  |  | Missing Status
AP-2026-02-22 | LIJ ORs - Cybernet + GCX Arm Deployment (Day 2 of 2) | 2026-02-22 | 8:00 | 18:00 | Local | Alejandro Perales; Chris Cummings; Patricia Marrero; Delroy Harris; Valentyn Nykoliuk | Rich Perez; Tim Seeberger | LIJ Main - OR Suite | Busy | 15 | Continue LIJ ORs deployment/testing. FIRST ACTION: confirm PA creds still working (or re-activate if needed). Same standards: GCX arms + peripherals installed; validate badge/barcode/connectivity; trackers stay live; close out open issues from Day 1. | 1) 08:00 kickoff + review Day 1 exceptions 2) Confirm PA creds active + quick verification 3) Stage remaining devices/parts 4) Complete remaining ORs first 5) Re-test any problem rooms 6) Update trackers continuously + resolve/escalate exceptions 7) Consolidate disposal pile + label clearly 8) 17:30 final sweep + handoff notes | Zero “we’ll fix it later” devices left in service. PA creds verified before work begins. Any blocker gets an owner + next action logged before wrap. Tracker stays current throughout execution. | 08:00 kickoff; 08:10 PA creds verification; 08:20 staging; 09:00 deployments rolling; 15:30 begin closeout/retests; 17:30 handoff notes; 18:00 wrap | No improvising changes; keep OR sequence disciplined; escalate access/port issues immediately; keep cabling clean and standardized; update trackers as we go so status is always current. | PA creds verified; all remaining assigned devices deployed + validated; Day 1 issues resolved or owned; tracker current; closeout notes sent. | Purpose Continue LIJ ORs deployment/testing. FIRST ACTION: confirm PA creds still working (or re-activate if needed). Same standards: GCX arms + peripherals installed; validate badge/barcode/connectivity; trackers stay live; close out open issues from Day 1. Stops (in order) 1) 08:00 kickoff + review Day 1 exceptions 2) Confirm PA creds active + quick verification 3) Stage remaining devices/parts 4) Complete remaining ORs first 5) Re-test any problem rooms 6) Update trackers continuously + resolve/escalate exceptions 7) Consolidate disposal pile + label clearly 8) 17:30 final sweep + handoff notes To-Do (hard requirements) Zero “we’ll fix it later” devices left in service. PA creds verified before work begins. Any blocker gets an owner + next action logged before wrap. Tracker stays current throughout execution. Suggested Timeline 08:00 kickoff; 08:10 PA creds verification; 08:20 staging; 09:00 deployments rolling; 15:30 begin closeout/retests; 17:30 handoff notes; 18:00 wrap Guardrails No improvising changes; keep OR sequence disciplined; escalate access/port issues immediately; keep cabling clean and standardized; update trackers as we go so status is always current. Completion signals PA creds verified; all remaining assigned devices deployed + validated; Day 1 issues resolved or owned; tracker current; closeout notes sent. |  |  |  | Missing Status
DD-2026-02-26 | LIJ - Deployment Kit Delivery + Staging (Day 1 of 2) | 2026-02-26 | 9:00 | 17:00 | Local | Deployment Delivery; Marvin Tate; Alejandro Perales | Rich Perez; Tim Seeberger | LIJ Main - Procedural Areas + Annex | Busy | 15 | Deliver and stage everything needed for the weekend deployment (13 procedural devices + 3 annex). Confirm counts, label/stage by area, and clear access blockers early. | 1) Pickup/pack check (kits, peripherals, labels) 2) Transport to LIJ 3) Stage procedural-area kits (13) 4) Stage annex kits (3) 5) Verify inventory against picklist 6) Identify + log blockers (missing parts, access, storage) 7) End-of-day handoff notes | All deployment kits (devices, arms, cables/peripherals), printed picklists, labels/tape, carts, access/keys, storage/staging space confirmed, tracker updated in real time. | 09:00 kickoff + loadout; 10:30 arrive LIJ + staging begins; 12:30 inventory checkpoint; 15:30 re-check counts + label sweep; 16:45 handoff notes + blocker escalation; 17:00 wrap. | No surprises on Saturday: if something is missing or access is blocked, escalate same day. Keep procedural vs annex kits separated and labeled. Update tracker as you go. | All items delivered + staged; kits labeled by area (13 procedural / 3 annex); discrepancies logged with owners + next actions; tracker reflects reality. | Purpose Deliver and stage everything needed for the weekend deployment (13 procedural devices + 3 annex). Confirm counts, label/stage by area, and clear access blockers early. Stops (in order) 1) Pickup/pack check (kits, peripherals, labels) 2) Transport to LIJ 3) Stage procedural-area kits (13) 4) Stage annex kits (3) 5) Verify inventory against picklist 6) Identify + log blockers (missing parts, access, storage) 7) End-of-day handoff notes To-Do (hard requirements) All deployment kits (devices, arms, cables/peripherals), printed picklists, labels/tape, carts, access/keys, storage/staging space confirmed, tracker updated in real time. Suggested Timeline 09:00 kickoff + loadout; 10:30 arrive LIJ + staging begins; 12:30 inventory checkpoint; 15:30 re-check counts + label sweep; 16:45 handoff notes + blocker escalation; 17:00 wrap. Guardrails No surprises on Saturday: if something is missing or access is blocked, escalate same day. Keep procedural vs annex kits separated and labeled. Update tracker as you go. Completion signals All items delivered + staged; kits labeled by area (13 procedural / 3 annex); discrepancies logged with owners + next actions; tracker reflects reality. |  |  |  | Missing Status
DD-2026-02-27 | LIJ - Deployment Kit Delivery + Staging (Day 2 of 2) | 2026-02-27 | 9:00 | 17:00 | Local | Deployment Delivery; Marvin Tate; Alejandro Perales | Rich Perez; Tim Seeberger | LIJ Main - Procedural Areas + Annex | Busy | 15 | Finalize staging, resolve gaps from Day 1, and confirm Saturday go-live readiness (parts, access, storage, and area readiness). | 1) Review Day 1 discrepancies 2) Deliver remaining items 3) Re-verify staged kits (procedural + annex) 4) Confirm access + storage plan for weekend 5) Final label/organization sweep 6) Confirm kickoff logistics for Saturday 7) Handoff notes | Open discrepancy list from Day 1, any missing parts, confirmed access badges/permissions, updated tracker, weekend contact list. | 09:00 kickoff + discrepancy triage; 10:30 deliver remaining items; 12:00 full recount checkpoint; 15:30 final staging sweep; 16:30 confirm Saturday kickoff + comms; 17:00 wrap. | If a blocker survives Friday, it will bite on Saturday. Escalate early. Keep kits sealed/organized after verification. | All discrepancies resolved or owned; kits staged + verified; Saturday kickoff plan confirmed; tracker current. | Purpose Finalize staging, resolve gaps from Day 1, and confirm Saturday go-live readiness (parts, access, storage, and area readiness). Stops (in order) 1) Review Day 1 discrepancies 2) Deliver remaining items 3) Re-verify staged kits (procedural + annex) 4) Confirm access + storage plan for weekend 5) Final label/organization sweep 6) Confirm kickoff logistics for Saturday 7) Handoff notes To-Do (hard requirements) Open discrepancy list from Day 1, any missing parts, confirmed access badges/permissions, updated tracker, weekend contact list. Suggested Timeline 09:00 kickoff + discrepancy triage; 10:30 deliver remaining items; 12:00 full recount checkpoint; 15:30 final staging sweep; 16:30 confirm Saturday kickoff + comms; 17:00 wrap. Guardrails If a blocker survives Friday, it will bite on Saturday. Escalate early. Keep kits sealed/organized after verification. Completion signals All discrepancies resolved or owned; kits staged + verified; Saturday kickoff plan confirmed; tracker current. |  |  |  | Missing Status
AP-2026-02-28 | LIJ ORs - Cybernet + GCX Arm Deployment (Day 1 of 2) | 2026-02-28 | 8:00 | 18:00 | Local | Alejandro Perales; Patricia Marrero; Valentyn Nykoliuk; Marvin Tate | Rich Perez; Tim Seeberger | LIJ Main - Procedural Areas | Busy | 15 | Deploy and validate devices in LIJ procedural areas (target: 13). First action: confirm PA creds/access for all techs before touching anything. | 1) 08:00 kickoff + scope confirm 2) Confirm PA creds active + quick verification 3) Stage devices/parts by room 4) Deploy in waves; validate peripherals + connectivity 5) Update tracker continuously 6) Resolve/escalate exceptions 7) End-of-day sweep + handoff notes | PA creds verified, deployment kits staged, barcode/badge readers tested, network/connectivity validated, trackers ready, room access confirmed. | 08:00 kickoff; 08:15 PA cred verification; 08:30 staging; 09:00 deployments rolling; 12:30 checkpoint; 16:30 start sweep; 17:30 handoff notes; 18:00 wrap. | No scope creep. Keep tracker honest. Escalate access/permissions blockers immediately. Separate ‘done’ vs ‘needs follow-up’. | Procedural-area deployments complete/validated (13 target); tracker accurate; exceptions logged with owners + next actions; clean handoff. | Purpose Deploy and validate devices in LIJ procedural areas (target: 13). First action: confirm PA creds/access for all techs before touching anything. Stops (in order) 1) 08:00 kickoff + scope confirm 2) Confirm PA creds active + quick verification 3) Stage devices/parts by room 4) Deploy in waves; validate peripherals + connectivity 5) Update tracker continuously 6) Resolve/escalate exceptions 7) End-of-day sweep + handoff notes To-Do (hard requirements) PA creds verified, deployment kits staged, barcode/badge readers tested, network/connectivity validated, trackers ready, room access confirmed. Suggested Timeline 08:00 kickoff; 08:15 PA cred verification; 08:30 staging; 09:00 deployments rolling; 12:30 checkpoint; 16:30 start sweep; 17:30 handoff notes; 18:00 wrap. Guardrails No scope creep. Keep tracker honest. Escalate access/permissions blockers immediately. Separate ‘done’ vs ‘needs follow-up’. Completion signals Procedural-area deployments complete/validated (13 target); tracker accurate; exceptions logged with owners + next actions; clean handoff. |  |  |  | Missing Status
AP-2026-03-01 | LIJ ORs - Cybernet + GCX Arm Deployment (Day 2 of 2) | 2026-03-01 | 8:00 | 18:00 | Local | Alejandro Perales; Chris Cummings; Patricia Marrero; Delroy Harris; Valentyn Nykoliuk | Rich Perez; Tim Seeberger | LIJ Main - Annex Area | Busy | 15 | Complete remaining deployments and validation, with focus on annex devices (target: 3) plus final hospital-wide sweep and closeout. | 1) 08:00 kickoff + review Day 1 exceptions 2) Confirm PA creds/access 3) Deploy/validate annex devices (3 target) 4) Re-validate any Day 1 follow-ups 5) Final sweep + reconcile tracker 6) Consolidate disposal/returns 7) Handoff notes + closeout | Annex access confirmed, remaining kits staged, exception list from Day 1, tracker current, packing materials for returns/disposal. | 08:00 kickoff; 08:15 review exceptions; 09:00 annex deployments; 12:30 checkpoint; 15:30 reconcile + sweep; 17:30 handoff notes; 18:00 wrap. | Close loops, don’t create new ones. Keep annex vs procedural records separate. Tracker stays current. | Annex deployments complete/validated (3 target); all exceptions owned; tracker reconciled; final closeout notes delivered. | Purpose Complete remaining deployments and validation, with focus on annex devices (target: 3) plus final hospital-wide sweep and closeout. Stops (in order) 1) 08:00 kickoff + review Day 1 exceptions 2) Confirm PA creds/access 3) Deploy/validate annex devices (3 target) 4) Re-validate any Day 1 follow-ups 5) Final sweep + reconcile tracker 6) Consolidate disposal/returns 7) Handoff notes + closeout To-Do (hard requirements) Annex access confirmed, remaining kits staged, exception list from Day 1, tracker current, packing materials for returns/disposal. Suggested Timeline 08:00 kickoff; 08:15 review exceptions; 09:00 annex deployments; 12:30 checkpoint; 15:30 reconcile + sweep; 17:30 handoff notes; 18:00 wrap. Guardrails Close loops, don’t create new ones. Keep annex vs procedural records separate. Tracker stays current. Completion signals Annex deployments complete/validated (3 target); all exceptions owned; tracker reconciled; final closeout notes delivered. |  |  |  | Missing Status
NC-2026-03-02 | LIJ SDF - Neuron Capsule Variable Testing | 2026-03-02 | 10:30 | 15:00 | Local | Neuron Capsules; LIJ SDF Tech | Jay Hernandez; Rich Perez | LIJ SDF - Satellite Dialysis Facility | Busy | 15 | Test variables on neuron capsules at LIJ SDF. Tech arrives early for setup; testing starts 11:00; capture results + next actions before wrap. | 1) 10:30 arrival + setup/check-in 2) 11:00 start testing per test plan 3) Log results/observations as you go 4) Midpoint checkpoint + adjust 5) Wrap-up: summarize findings + next steps 6) Clean handoff and secure equipment | Capsules + peripherals, test plan, logging template, access confirmed, any required credentials, spare cables/batteries. | 10:30 setup; 11:00 testing start; 12:30 checkpoint; 14:30 consolidate notes; 15:00 wrap. | No ad-hoc changes without logging. Keep a clear chain of custody for devices. Escalate any safety/clinical access issues immediately. | Tested planned variables; results logged; follow-ups assigned; equipment accounted for. | Purpose Test variables on neuron capsules at LIJ SDF. Tech arrives early for setup; testing starts 11:00; capture results + next actions before wrap. Stops (in order) 1) 10:30 arrival + setup/check-in 2) 11:00 start testing per test plan 3) Log results/observations as you go 4) Midpoint checkpoint + adjust 5) Wrap-up: summarize findings + next steps 6) Clean handoff and secure equipment To-Do (hard requirements) Capsules + peripherals, test plan, logging template, access confirmed, any required credentials, spare cables/batteries. Suggested Timeline 10:30 setup; 11:00 testing start; 12:30 checkpoint; 14:30 consolidate notes; 15:00 wrap. Guardrails No ad-hoc changes without logging. Keep a clear chain of custody for devices. Escalate any safety/clinical access issues immediately. Completion signals Tested planned variables; results logged; follow-ups assigned; equipment accounted for. |  |  |  | Missing Status
PM-2026-02-24 | LIJ - iPhones Team Coverage (Patricia Marrero onsite) | 2026-02-24 | 8:00 | 17:00 | Local | Patricia Marrero | Nicholas Valentin (remote); Jay Hernandez | LIJ | Busy | 15 | Coverage for Jay Hernandez at LIJ. Nicholas Valentin provides remote support today as needed. | 1) AM check-in with Jay/Hospital stakeholders 2) Cover tickets/issues 3) Document handoffs 4) EOD status update | Access/credentials, ticket queue access, contact list, escalation path. | 08:00 check-in; 12:00 midpoint status; 16:30 handoff notes; 17:00 wrap. | Escalate blockers early; keep notes crisp; ensure handoff continuity. | Coverage provided; issues progressed/resolved; handoff notes posted. | Purpose Coverage for Jay Hernandez at LIJ. Nicholas Valentin provides remote support today as needed. Stops (in order) 1) AM check-in with Jay/Hospital stakeholders 2) Cover tickets/issues 3) Document handoffs 4) EOD status update To-Do (hard requirements) Access/credentials, ticket queue access, contact list, escalation path. Suggested Timeline 08:00 check-in; 12:00 midpoint status; 16:30 handoff notes; 17:00 wrap. Guardrails Escalate blockers early; keep notes crisp; ensure handoff continuity. Completion signals Coverage provided; issues progressed/resolved; handoff notes posted. |  |  |  | Missing Status
CH-2026-02-25 | LIJ - iPhones Team Coverage (Cyen Heyliger onsite) | 2026-02-25 | 8:00 | 17:00 | Local | Cyen Heyliger | Jay Hernandez | LIJ | Busy | 15 | Coverage for Jay Hernandez at LIJ. | 1) AM check-in 2) Cover tickets/issues 3) Document handoffs 4) EOD status update | Access/credentials, ticket queue access, contact list. | 08:00 check-in; 12:00 midpoint status; 16:30 handoff notes; 17:00 wrap. | Keep handoffs tight; escalate blockers early. | Coverage provided; handoff notes posted. | Purpose Coverage for Jay Hernandez at LIJ. Stops (in order) 1) AM check-in 2) Cover tickets/issues 3) Document handoffs 4) EOD status update To-Do (hard requirements) Access/credentials, ticket queue access, contact list. Suggested Timeline 08:00 check-in; 12:00 midpoint status; 16:30 handoff notes; 17:00 wrap. Guardrails Keep handoffs tight; escalate blockers early. Completion signals Coverage provided; handoff notes posted. |  |  |  | Missing Status
PM-2026-02-26 | LIJ - iPhones Team Coverage (Patricia Marrero onsite) | 2026-02-26 | 8:00 | 17:00 | Local | Patricia Marrero | Jay Hernandez | LIJ | Busy | 15 | Coverage for Jay Hernandez at LIJ. | 1) AM check-in 2) Cover tickets/issues 3) Document handoffs 4) EOD status update | Access/credentials, ticket queue access, contact list. | 08:00 check-in; 12:00 midpoint status; 16:30 handoff notes; 17:00 wrap. | Keep handoffs tight; escalate blockers early. | Coverage provided; handoff notes posted. | Purpose Coverage for Jay Hernandez at LIJ. Stops (in order) 1) AM check-in 2) Cover tickets/issues 3) Document handoffs 4) EOD status update To-Do (hard requirements) Access/credentials, ticket queue access, contact list. Suggested Timeline 08:00 check-in; 12:00 midpoint status; 16:30 handoff notes; 17:00 wrap. Guardrails Keep handoffs tight; escalate blockers early. Completion signals Coverage provided; handoff notes posted. |  |  |  | Missing Status
CH-2026-02-27 | LIJ - iPhones Team Coverage (Cyen Heyliger onsite) | 2026-02-27 | 8:00 | 17:00 | Local | Cyen Heyliger | Jay Hernandez | LIJ | Busy | 15 | Coverage for Jay Hernandez at LIJ. | 1) AM check-in 2) Cover tickets/issues 3) Document handoffs 4) EOD status update | Access/credentials, ticket queue access, contact list. | 08:00 check-in; 12:00 midpoint status; 16:30 handoff notes; 17:00 wrap. | Keep handoffs tight; escalate blockers early. | Coverage provided; handoff notes posted. | Purpose Coverage for Jay Hernandez at LIJ. Stops (in order) 1) AM check-in 2) Cover tickets/issues 3) Document handoffs 4) EOD status update To-Do (hard requirements) Access/credentials, ticket queue access, contact list. Suggested Timeline 08:00 check-in; 12:00 midpoint status; 16:30 handoff notes; 17:00 wrap. Guardrails Keep handoffs tight; escalate blockers early. Completion signals Coverage provided; handoff notes posted. |  |  |  | Missing Status
end

## Correspondence Ledger
# | Workstream / Thread | Subject | Purpose | Status | Waiting on | Next move
1 | Glen Cove W2 MIB Cards / DS8178 Programming + Epic Validation | RE: Glen Cove Hsp W2 MIB Cards PO 7025040707 - Monday, 1/26 and Tuesday, 1/27 Installation | Thank Akbar, validate his one-pager, quietly add your expanded companion guide, set an update loop | SENT (per your note) | Any corrections/updates to Akbar’s 1-pager | If no response but field issues appear, reply with the specific symptom + point to the relevant section of your companion guide
2 | REQ1282033 — SIUH Anesthesia Carts / Serial Cables (SPEC999015) | REQ1282033 (SIUH) — Serial cable requirement + procurement next steps (SPEC999015) | Lock: swap vs addition, final qty (2 vs 4), procurement owner, ship-to, needed-by | DRAFTED | Tim/Steve/Mohamed/Akbar confirmation | Send. Then track: qty, quote owner, requisition owner, ETA, delivery confirmation
3 | Epic Beans Device Type Test — CDW Tech Onsite (SDF) | Epic Beans Device Type Test (SDF) — Confirm readiness, roles, and pass/fail plan for Mon 1/26 12:00–2:30 | Convert invite into an executable test plan: pass/fail owner + rollback owner | DRAFTED | Epic point person + rollback owner confirmation | Send. Then add a one-line “go/no-go” confirmation request morning-of
4 | LIJ Cybernet — 80 units (scope mapping) | LIJ Cybernet (80) — Facility mapping + wave counts needed to stage correctly (due 02/06) | Force “LIJ” into facility mapping + qty per wave + neuron scope clarity | DRAFTED | Tim confirmation on LIJ mapping + wave quantities | Send. Then update your tracker with mapping IDs (LIJMC-NHP vs LIJ-VS vs LIJ-FH etc.)

## unwired teams invite tab
Event ID | MV-2026-01-11
Title
Date
Time | –
Location
Teams Body (copy/paste) | (click cell below, Ctrl+A, Ctrl+C)

## IP-2026-01-12
Field | Drop-in
Title | iPhone/Rover — Recurring Training Block (Starts Week of 1/12)
Required attendees | Emmanuel Sanchez; Ezekiel; Erik Guzman; Julio Mojica; Asher Ali; Valentyn Nykoliuk; Tanjim Khan; Shazaib Idrees; Cyen Heyliger; Connor Hoffman
Optional attendees | Nayelin Monegro; Rich Perez
Date | 2026-01-12
Start / End | 9:00 AM – 6:00 PM (Mon–Fri) — recurring starting 1/12
Show as | Busy
Location | Training window (no meeting link)
Reminder | 30 minutes
Description / Body | iPhone/Rover Shadow Training — Recurring Block (Starts Week of 1/12) This is a training window, not a meeting. Use this block to schedule and complete shadow sessions. No one needs to join. What this is: A recurring training window for iPhone/Rover shadowing + skill-building. Each trainee completes at least 1–2 shadow blocks to start, then continues as needed. Knowledge gaps get logged and tracked. Mentors: • Emmanuel Sanchez (Lenox Hill) • Erik Guzman (PBMC) • Ezekiel (Staten Island N&S) Trainees: • Julio Mojica • Asher Ali • Valentyn Nykoliuk • Tanjim Khan • Shazaib Idrees • Cyen Heyliger • Connor Hoffman TRAINEES — DO THIS Send your mentor: • Two time windows next week you can shadow (and more as needed) • Your main site • Any constraints (access issues, hard stop time, etc.) After each shadow block: • Update the Training Log the same day (what was covered + knowledge gaps + next topic) MENTORS — DO THIS • Tell me how many trainees you can actively support at a time • Coordinate shadow blocks with those trainees • Update the Training Log with: Trainee / Mentor / Date-Time / Site / What was covered / Knowledge gaps & blockers / Next recommended topic RULE Training Log is the source of truth. No side chats as the “real plan.”
Checkpoints / Completion signals | • Trainee/mentor connections made and first shadow block scheduled • Training Log updated same day after each shadow block • Knowledge gaps captured and follow-up topics assigned

## Khadejah 1-8-2026
Field | Drop-in
Title | Khadejah — Inventory Counts + Locations (1 Marcus + HQ) + Pallets + Arm Attach Doc (1/8)
Required attendees | Khadejah Harrison
Optional attendees | Rich Perez ; Bonita Outlaw
Date | 2026-01-08
Start / End | 8:00 AM – 5:00 PM (adjust to your real hours)
Show as | Busy
Location | HQ + 1 Marcus (multi-stop; see agenda)
Reminder | 30 minutes
Description / Body | Objective - Establish a single reliable view of what we have and where it is (HQ + 1 Marcus), including pallet stock, so we can forecast deployment trajectory. To-Do (checklist) ☐ Start in HQ: sweep all staging zones + pallets; log COUNT + EXACT LOCATION for each item (prioritize Neurons + arms first) ☐ Tag pallets as P-001 / P-002 / … and record contents (at least Neurons + arms per pallet) ☐ Repeat the same sweep at 1 Marcus; log counts + exact locations ☐ Update Inventory Master (single source of truth): consolidate counts; mark CONFLICTs; timestamp LastCounted + CountedBy ☐ Arm→Neuron attach: capture steps (clean angles) + note any tools/hardware required ☐ Send EOD summary to Rich: HQ vs 1 Marcus totals, pallet status, shortages/blockers, runway for upcoming sites Location format (use exactly) [SITE] - [AREA] - [SUBAREA] Example: HQ - Config Desks - Under Desk Row A Guardrails - No guessing. If unsure, mark UNKNOWN/CONFLICT and note why. - Don’t move stock without updating its location in the master.
Checkpoints / Completion signals | Counts + locations captured for HQ and 1 Marcus (Neurons + arms minimum) Pallets tagged + recorded Inventory Master updated + timestamped Arm attach steps captured + shared EOD summary sent to Rich

## Alejandro 1-8-2026
Field | Drop-in
Title | Alejandro — 3HQ Key Drop + HQ Plainview Config + PBMC Prep (1/8)
Required attendees | Alejandro Perales
Optional attendees | Ralph (3HQ) ; Khadejah Harrison ; Akbar (if he’s the config owner)
Date | 2026-01-08
Start / End | 8:00 AM – 5:00 PM (adjust to your real hours)
Show as | Busy
Location | HQ — Plainview (multi-stop details in agenda)
Reminder | 30 minutes
Description / Body | Purpose - Execute the 1/8 run: return universal key, configure devices at HQ Plainview, stage for PBMC deployment readiness, and align counts with Khadejah. Stops (in order) 1) 3HQ - Key drop with Ralph 2) HQ - Plainview - Device configuration + staging 3) PBMC - Deployment prep / readiness To-Do (hard requirements) - Contact Ralph first thing AM to coordinate key handoff (time + exact meetup spot). - Drop off universal key to Ralph at 3HQ and confirm receipt. - Head to HQ Plainview ASAP after key drop. - Configure devices at HQ (confirm which units require config vs already prepped). - Stage/pack for PBMC deployment (devices + required cables/adapters + spares). - Before deployment: sync with Khadejah on counts and reconcile any gaps. Suggested Timeline (adjust as needed) - 8:00-8:15 Call/text Ralph; lock handoff details - 8:15-9:00 3HQ key drop -> confirm receipt - 9:00-1:00 HQ Plainview: configure devices + verification checks - 1:00-2:00 Staging/packout for PBMC (labeling + inventory sanity check) - 2:00-2:15 Quick sync w/ Khadejah: counts + deployment plan - 2:15+ Travel/prepare for PBMC deployment window Guardrails (avoid scope creep) - If Tim is involved on install timing: meet at the requested time, but confirm requirements in advance. - Do not accept extra add-ons without approval - log requests and escalate. Completion signals (message back in Teams chat) - Key returned to Ralph + time - HQ config complete + device count - PBMC staging complete + any blockers - Counts aligned with Khadejah + final count
Checkpoints / Completion signals | Key returned to Ralph @ ____ (time) HQ config complete - ____ devices PBMC staging complete - blockers: ____ / none Counts aligned with Khadejah - final count ____

## Julio 1-8-2026
Field | Drop-in
Title | Julio — Arms Transport + Spreadsheet Updates + Assist Counts (HQ / 1 Marcus) (1/8)
Required attendees | Julio Mojica
Optional attendees | Khadejah Harrison ; Rich Perez
Date | 2026-01-08
Start / End | 8:00 AM – 5:00 PM (adjust to real hours)
Show as | Busy
Location | HQ + 1 Marcus (multi-stop; see checklist)
Reminder | 30 minutes
Description / Body | Objective: Transport arms, log them in the master spreadsheet, then assist Khadejah with counts. Checklist: (1) Transport arms (2) Add arms into spreadsheet (qty + exact location) (3) Assist Khadejah with counts. Coordination: Coordinate with Julio after transport to work out counts on-site without extra driving; stop by 1 Marcus first only if it reduces back-and-forth. Completion: Arms delivered + logged; counts advanced; blockers flagged; status sent.
Status | Planned

## Picklists
ShowAs | Status | ReminderMinutes | TimeZone
Busy | Planned | 5 | Local
Free | In Progress | 10 | America/New_York
Tentative | Blocked | 15
Out of Office | Done | 30
60
120

## Drop-ins
Audience | Use | Message (copy/paste) | Completed
Ralph | AM coordination | Morning Ralph - Alejandro Perales is dropping off the universal key today. What time + meetup spot at 3HQ works best? He'll confirm once it's handed off. | Yes
Alejandro | Run order / checkpoints | Today's run order: 1) Contact Ralph now, lock handoff details 2) Drop key at 3HQ + confirm receipt 3) Head to HQ Plainview ASAP 4) Configure + stage devices for PBMC 5) Sync with Khadejah on counts before deployment Ping after each checkpoint (Key / HQ config / Staging / Counts). | Yes
Khadejah | Counts sync | Quick sync today - when you have a window, send your latest counts + any gaps. Alejandro will align staging with your numbers before deployment. | Yes
Bonita | FYI update | FYI: Alejandro is returning the universal key to Ralph at 3HQ this morning, then heading to HQ Plainview for config + PBMC staging. I'll flag any blockers. | Yes