## Contributions & Wins
NSUH OR Device Integration – Contributions & Wins
Executive summary of validated operational wins, workflow improvements, and lessons learned supporting NSUH device integration.
Operational Contributions and Workflow Advancements
Category | Owner | Action | Impact | System Effect
System Recovery | Richard Perez | Identified posting as the resolution for the COM port allocation lock in Device Manager, restoring COM port allocations on affected devices. | Restored device usability and removed a blocker from active OR integrations. | Prevented configuration bottlenecks and reduced repeated troubleshooting.
Access Workaround | Alejandro | Developed workarounds for Epic TDR access limitations and constraints. Created and refined SOPs, guides, and tooling. | Enabled continued survey and configuration workflow despite access gaps. | Maintained deployment velocity without waiting on external dependencies.
Installation Standardization | Alejandro, Khadejah | Refined SIS installation steps, cable management standards, adhesive feasibility decisions, application configurations, and QA expectations. | Reduced variability across technicians and improved deployment uniformity. | Established a more repeatable installation and quality-assurance workflow.
Workflow Enforcement | Khadejah | Maintained strict adherence to configuration, deployment, ticketing, and client correspondence processes at each step. | Prevented missed steps and rework. | Ensured consistency and quality control across the workflow.
Problem Resolution | Khadejah, Geoff | Resolved domain rejoin issues and documented the working approach. Created SOPs and file shares to facilitate workflow with pressing deadlines. Created standardized tooling to normalize naming conventions and deadline projections. | Restored device readiness efficiently. | Streamlined the domain rejoin process for broader team use.
Inventory Systemization | Khadejah | Converted a disorganized equipment area into a structured, categorized staging environment by separating hardware types, consolidating loose items, labeling boxes, grouping systems, and clearing workspace for continued organization readiness. | Restored visibility, reduced search time, and improved access to deployment-critical components. | Established a stronger foundation for inventory tracking, redeployment readiness, and scalable logistics workflow.
Process Development | Richard Perez | Trained team members and developed structured reporting for leadership visibility and operational control. | Improved team capability and visibility. | Enabled scalable workflow and reporting clarity.
Lesson learned: ✔️ (Valentine’s Day) | Richard Perez, Alejandro | Always ensure staffing includes a float while advancing deployments. | Reduced downstream rework, late clock-outs, and avoidable OT exposure. | Improved deployment continuity and staffing resilience during execution.
Tooling & Automation | Geoff | Developed Excel-based tools embedded within the team’s internal tracker. Created standardized tooling to normalize naming conventions and deadline projections. | Improved data capture efficiency and reduced manual entry errors | Integrated tooling into operational workflow, increasing consistency and scalability

## Billing Summary - Mar 2026
Mar 2026 - Northwell Billing Summary
Manager-facing rollup for Neuron labor plus Delivery / Transport / Disposal tied to the same Northwell project.
Billing Bucket | Tech Count | Worked Days | Billable Hours
Neurons | 12 | 167 | 1463.75
Delivery / Transport / Disposal | 3 | 12 | 108
Combined Northwell billing | 15 | 179 | 1571.75
Aamir Ali, Aatif Ali, and Abdul Gopang roll under Delivery / Transport / Disposal and should be billed to Northwell under the same project effort.
Neuron Deployments by Tech |  |  |  | Delivery / Transport / Disposal by Tech
Staff Name | Worked Days | Billable Hours | Billing Note | Staff Name | Worked Days | Billable Hours
Rich Perez | 30 | 376.27 | Bill to Northwell - Neurons | Aamir Ali | 4 | 36
Geoff Gerber | 24 | 222.17 | Bill to Northwell - Neurons | Aatif Ali | 4 | 36
Khadejah Harrison | 17 | 212.53 | Bill to Northwell - Neurons | Abdul Gopang | 4 | 36
Asher Ali | 20 | 163.15 | Bill to Northwell - Neurons | Transport Total | 12 | 108
Alejandro Perales | 25 | 141.32 | Bill to Northwell - Neurons
Valentyn Nykoliuk | 9 | 87 | Bill to Northwell - Neurons
Patricia Marrero | 11 | 84.9 | Bill to Northwell - Neurons
Emmanuel Sanchez | 9 | 58.67 | Bill to Northwell - Neurons
Christopher Cummings | 14 | 42.75 | Bill to Northwell - Neurons
Cyen Heyliger | 6 | 50.5 | Bill to Northwell - Neurons (manual March map)
Cristian Munoz | 1 | 15.5 | Bill to Northwell - Neurons
Julio Mojica | 1 | 9 | Bill to Northwell - Neurons
Neuron Total | 167 | 1463.75
Audit trail: all rollups above pull from Billing Detail - Mar 2026, normalized to one row per tech per worked day, with Cyen Heyliger manually mapped into Neurons for March.
Audit trail: Billing Detail - Mar 2026

## Exec KPI - 2026-04-04
Exec KPI - 2026-04-04 ¦ NSUH Deployment Summary
Weekday work: 1 Marcus configuration + inventory count ¦ Weekend work: NSUH deployment + QA ¦ Tracker-driven summary with explicit 4/4 deployment ownership.
Site Summary
Site | Weighted Task Hrs | Deployment Hrs | QA / Validation Hrs | Incident Hrs | Other Hrs | Devices Deployed | QA Devices | Basis
NSUH | 74.7 | 28 | 11.7 | 10.1 | 7.4 | 15 | 15 | Weekend deployment + QA
1 Marcus | 45.5 | 0 | 23 | 0 | 22.5 | 0 | 0 | Weekday configuration + inventory count
Total | 120.2 | 28 | 34.7 | 10.1 | 29.9 | 15 | 15
Weighted Task Hours by Technician
Tech | Weighted Task Hrs | Deployment Hrs | QA / Validation Hrs | Incident Hrs | Other Hrs | Devices Deployed | QA Devices | Scope
Alejandro Perales | 34.7 | 0 | 34.7 | 0 | 0 | 0 | 15 | Weekday configuration + Saturday QA
Asher Ali | 8 | 8 | 0 | 0 | 0 | 5 | 0 | Deployment
Geoff Gerber | 40.7 | 2 | 0 | 32.1 | 6.6 | 0 | 0 | Incident + field support
Emmanuel Sanchez | 8 | 8 | 0 | 0 | 0 | 0 | 0 | Field support
Khadejah Harrison | 5.5 | 0 | 0 | 0 | 5.5 | 0 | 0 | Workflow control
Valentyn Nykoliuk | 11.8 | 2 | 9.8 | 0 | 0 | 0 | 0 | Config support
Patricia Marrero | 6 | 6 | 0 | 0 | 0 | 0 | 0 | Field support
Christopher Cummings | 13.5 | 0 | 0 | 0 | 13.5 | 0 | 0 | Weekday inventory count / Marcus
Julio Mojica | 9 | 0 | 0 | 0 | 9 | 0 | 0 | Weekday inventory count / Marcus
Deployment Ownership - Saturday 2026-04-04
Person | Deployment Date | Site | Devices Deployed | QA Devices | Role | Source | Notes
Alejandro Perales | 2026-04-04 | NSUH | 0 | 15 | QA / readiness | User-confirmed split | Subject matter expert.
Rich Perez | 2026-04-04 | NSUH | 5 | 0 | Management / Deployment / Survey | User-confirmed split | Subject matter expert.
Delroy Harris | 2026-04-04 | NSUH | 5 | 0 | Deployment | User-confirmed split | Smart hands
Asher Ali | 2026-04-04 | NSUH | 5 | 0 | Deployment / Survey | User-confirmed split | Smart hands

## Live - Mar 2026
Mar 2026 - Attendance (Live)
Staff Name | Project | Mar 01 - Clock In | Mar 01 - Clock Out | Mar 02 - Clock In | Mar 02 - Clock Out | Mar 03 - Clock In | Mar 03 - Clock Out | Mar 04 - Clock In | Mar 04 - Clock Out | Mar 05 - Clock In | Mar 05 - Clock Out | Mar 06 - Clock In | Mar 06 - Clock Out | Mar 07 - Clock In | Mar 07 - Clock Out | Mar 08 - Clock In | Mar 08 - Clock Out | Mar 09 - Clock In | Mar 09 - Clock Out | Mar 10 - Clock In | Mar 10 - Clock Out | Mar 11 - Clock In | Mar 11 - Clock Out | Mar 12 - Clock In | Mar 12 - Clock Out | Mar 13 - Clock In | Mar 13 - Clock Out | Mar 14 - Clock In | Mar 14 - Clock Out | Mar 15 - Clock In | Mar 15 - Clock Out | Mar 16 - Clock In | Mar 16 - Clock Out | Mar 17 - Clock In | Mar 17 - Clock Out | Mar 18 - Clock In | Mar 18 - Clock Out | Mar 19 - Clock In | Mar 19 - Clock Out | Mar 20 - Clock In | Mar 20 - Clock Out | Mar 21 - Clock In | Mar 21 - Clock Out | Mar 22 - Clock In | Mar 22 - Clock Out | Mar 23 - Clock In | Mar 23 - Clock Out | Mar 24 - Clock In | Mar 24 - Clock Out | Mar 25 - Clock In | Mar 25 - Clock Out | Mar 26 - Clock In | Mar 26 - Clock Out | Mar 27 - Clock In | Mar 27 - Clock Out | Mar 28 - Clock In | Mar 28 - Clock Out | Mar 29 - Clock In | Mar 29 - Clock Out | Mar 30 - Clock In | Mar 30 - Clock Out | Mar 31 - Clock In | Mar 31 - Clock Out
Aamir Ali | Delivery / Transport / Disposal | 8:00 | 17:00 | [10 empty] | 8:00 | 17:00 | 8:00 | 17:00 | [12 empty] | 8:00 | 17:00
Aatif Ali | Delivery / Transport / Disposal | 8:00 | 17:00 | [10 empty] | 8:00 | 17:00 | 8:00 | 17:00 | [12 empty] | 8:00 | 17:00
Abdul Gopang | Delivery / Transport / Disposal | 8:00 | 17:00 | [10 empty] | 8:00 | 17:00 | 8:00 | 17:00 | [12 empty] | 8:00 | 17:00
Adam Pagan | 0
Alberto Montalvo | Projects Team
Alejandro Perales | Neuron Deployments |  |  |  |  | 10:00 | 14:30 | 12:45 | 14:20 | 11:20 | 14:25 | 10:30 | 14:10 | 7:20 | 19:00 |  |  | 8:45 | 14:40 | 6:15 | 14:30 | 11:35 | 14:30 | 2:00 | 5:05 | 10:10 | 14:30 | 7:30 | 21:30 | 10:00 | 11:59 | 12:00 | 13:30 | 0:30 | 5:00 | 2:00 | 5:30 | 2:00 | 6:00 | 0:00 | 5:00 | 7:20 | 22:30 | 7:30 | 18:30 | 23:50 | 4:00 | 23:55 | 2:00 |  |  | 1:55 | 9:50 |  |  | 7:00 | 18:00 | 8:00 | 14:00 | 9:00 | 9:30
Alexander Lent | 0
Alexander Sanchez | DSE
Alfonso Falcon | Neuron Deployments
Alinx Simon | Projects Team
Anthony Abijoh | iPhone Support
Anthony Spezio | DoE
Arin Budhram | 0
Asher Ali | Neuron Deployments | [6 empty] | 17:00 | 22:00 |  |  |  |  | 7:30 | 17:15 |  |  | 17:00 | 22:30 | 17:00 | 3:00 | 17:00 | 5:00 |  |  | 17:00 | 23:30 | 12:00 | 18:30 | 15:00 | 23:59 | 17:00 | 4:00 | 17:00 | 3:00 | 17:00 | 2:00 | 17:00 | 3:30 | PTO | PTO | 7:00 | 10:30 | 8:00 | 18:30 | 17:00 | 4:00 | 17:00 | 2:00 | 20:00 | 2:30 | 0:05 | 9:00 |  |  | 7:30 | 10:30 | 8:00 | 14:00
Caesar Olivas | DSE
Carl Romero-Salam | iPhone Support |  |  | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 |  |  |  |  | 8:00 | 17:00 | 8:00 | 17:00 | [10 empty] | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 |  |  |  |  | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 |  |  |  |  | 8:00 | 17:00 | 8:00 | 17:00
Christopher Cummings | Neuron Deployments |  |  | 16:00 | 18:00 | 16:00 | 18:00 | 16:00 | 18:00 | 16:00 | 18:00 | 16:00 | 18:00 |  |  |  |  | 15:15 | 22:30 | 16:00 | 18:00 | 16:00 | 18:00 | 16:00 | 18:00 | 16:00 | 18:00 |  |  |  |  | 16:00 | 18:00 | 16:00 | 18:00 | [20 empty] | 7:30 | 16:00 | 9:00 | 14:00
Clifford Joseph | iPhone Support
Connor Hoffman | iPhone Support
Cristian Munoz | Neuron Deployments | [40 empty] | 7:00 | 22:30
Cyen Heyliger | iPhone Support | [16 empty] | 9:00 | 17:00 | 8:00 | [27 empty] | 9:30 | 18:00 | 9:30 | 18:00 | 9:30 | 18:00 | 9:30 | 18:00 |  |  |  |  | 9:30 | 18:00 | 9:30
Delroy Harris | Projects Team
Devon Schoen | DSE
Dondre Blake | 0
Emmanuel Sanchez | Neuron Deployments | [20 empty] | 19:56 | 5:00 |  |  | 20:01 | 23:31 | 10:30 | 18:30 |  |  | 20:17 | 4:00 |  |  | 22:26 | 4:00 | [8 empty] | 21:00 | 4:00 | 21:00 | 2:00 |  |  | 20:37 | 2:30 |  |  | 11:04 | 18:00
Erik Guzman | 0
Faisal Hussain | Projects Team
Geoff Gerber | Neuron Deployments |  |  | 9:00 | 23:04 | 9:00 | 18:00 | 9:00 | 22:57 | 9:00 | 18:00 | 9:00 | 18:00 |  |  |  |  | 9:00 | 18:39 | 9:00 | 18:00 | 9:00 | 18:00 | 9:00 | 18:00 | 9:00 | 18:00 |  |  |  |  | 9:00 | 18:00 | 9:00 | 18:00 | 9:00 | 18:00 | 9:00 | 18:00 | 9:00 | 18:00 |  |  | 9:00 | 18:00 |  |  | 9:00 | 18:00 | 9:00 | 18:00 | 9:00 | 18:00 | 9:00 | 18:00 | 7:30 | 16:00 | 9:00 | 14:00 | 9:00 | 18:00 | 9:00 | 18:00
Gerian Beaubrun | 0
Jason Hernandez | iPhone Support
Julio Mojica | Neuron Deployments | [50 empty] | 9:00 | 18:00
Kareem Mohamed | 0
Katina Flemming | DSE
Khadejah Harrison | Neuron Deployments |  |  | 9:00 | 1:00 | 9:30 | 18:00 | 9:00 | 23:00 | 9:00 | 21:00 | 8:30 | 20:00 |  |  |  |  | 9:00 | 22:30 | 6:30 | 5:00 | 11:00 | 5:00 | 11:00 | 18:00 | 9:00 | 18:00 |  |  |  |  | 9:00 | 19:00 | 9:00 | 19:00 | 9:00 | 22:00 | 9:00 | 5:00 | 10:30 | 18:00 |  |  |  |  | 9:00 | 20:02 | 9:00 | 18:00
Khalidah Abdul-Rahim | Neuron Deployments
Logan Montalvo | 0
Mardoche Joseph | iPhone Support |  |  |  |  | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 |  |  |  |  | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 |  |  |  |  | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 |  |  |  |  | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 |  |  |  |  | 8:00 | 17:00 | 8:00 | 17:00
Marlon Caleb | 0
Martin Hammett | 0
Marvin Tate | Delivery / Transport / Disposal
Mathurin Soubeiga | DSE
Max Thomas | Projects Team
Md Suhan Newaz | 0
Michael Gahn | MacOS Support
Mohammad Umair | 24-Day
Mohammed Gousjan | DSE
Nasim Khan | DSE
Nicholas Valentin | Neuron Deployments
Patricia Marrero | Neuron Deployments |  |  | 9:38 | 18:00 | 9:54 | 18:03 | N/A | N/A | N/A | N/A | 9:53 | 18:00 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | 9:49 | 18:30 | 9:45 | 18:08 | 9:47 | 17:01 | N/A | N/A | 10:03 | 17:34 | 8:17 | 19:08 |  |  | N/A | N/A | 12:54 | 18:00 | N/A | N/A | 12:00 | 18:00 |  |  | 7:30 | 14:00
Rasab Ali | 0
Rezaul Roman | 0
Rich Perez | Neuron Deployments | 12:18 | 21:18 | 8:00 | 1:00 | 8:00 | 18:45 | 8:00 | 23:30 | 8:00 | 21:00 | 8:00 | 20:00 | 9:00 | 21:40 |  |  | 7:58 | 23:30 | 6:30 | 23:00 | 1:33 | 21:00 | 8:00 | 21:00 | 6:00 | 23:30 | 8:01 | 23:48 | 9:00 | 23:59 | 8:00 | 23:30 | 8:16 | 21:00 | 8:00 | 20:34 | 8:00 | 20:00 | 7:55 | 20:34 | 8:00 | 23:30 | 8:00 | 18:04 | 8:00 | 22:00 | 8:01 | 18:01 | 7:58 | 18:21 | 8:00 | 19:00 | 8:00 | 18:00 | 8:02 | 13:34 | 7:58 | 14:30 | 8:00 | 19:03 | 7:55 | 12:00
Saliou Diallo | iPhone Support |  |  | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 |  |  |  |  | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 |  |  |  |  | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 |  |  |  |  | 8:00 | 17:00 | 8:00 | 17:00 | 8:00 | 17:00 | 9:00 | 14:30 | 8:00 | 17:00 |  |  |  |  | 8:00 | 17:00 | 8:00 | 17:00
Shazaib Idrees | iPhone Support
Sheldon Brown | ReConnect
Tanjim Khan | iPhone Support
Thomas Bordon | 0
Valentyn Nykoliuk | Neuron Deployments | [20 empty] | 15:00 | 23:00 |  |  |  |  | 7:30 | 22:00 |  |  |  |  | 13:30 | 23:00 | 13:30 | 23:00 | [8 empty] | 14:00 | 23:00 | 14:00 | 23:00 |  |  | 18:00 | 23:00 |  |  | 7:00 | 21:30 |  |  |  |  | 15:00 | 23:00

## Event Log
Event Log ¦ Quantity, Duration, and Case-Linked Hours
One row = one atomic work event. Suggested Hours are formula-driven defaults. Actual Billed Hours are user-entered later. Use Case ID to tie the story together across dates.
Atomic Event Log
Event Date | Week Start | Person | Base of Operations | Room / Area | Case ID | Workstream | Event Type | Task Category | Quantity | Unit Type | Window Code | Std Hours / Unit | Fixed Overhead Hrs | Complexity Factor | Disruption Factor | Travel / Transit Hrs | Modeled Hours | Suggested Hours | Actual Billed Hours | Variance Hrs | Billable Flag | Narrative Tag | Primary Hostname | Related Asset / Hostname | Evidence Source | Notes
2026-02-21 | 2026-02-16 | Richard Perez | LIJ | Same room / anesthesia station area | LIJ-2026-02-21-RETURN-01 |  | Survey Blocked | Survey / Validation | 1 |  |  |  |  | 1.1 | 1.35 | 0 | [5 empty] | Risk | WNH270OPR432 | LIJ-MACH-D / SPARE | User-provided tracker screenshot + chat context | Tech could not complete the survey because the machine was abruptly displaced before completion.
2026-02-21 | 2026-02-16 | Richard Perez | LIJ | Same room / anesthesia station area | LIJ-2026-02-21-RETURN-01 |  | Client Follow-Up | Client Correspondence | 1 |  |  |  |  | 1 | 1.1 | 0 | [5 empty] | Client Touch | WNH270OPR432 | LIJ-MACH-D / SPARE | User-confirmed in chat (client correspondence not separately screenshot) | Client correspondence / return-visit coordination associated with incomplete survey and room-state issue.
2026-02-28 | 2026-02-23 | Richard Perez | LIJ | Same room / anesthesia station area | LIJ-2026-02-21-RETURN-01 |  | Return Dispatch / Logistics Move | Logistics | 1 |  |  |  |  | 1 | 1.05 | 0.75 | [5 empty] | Logistics | WNH270OPR403 | LIJ-MACH-D | User-provided chat context | Sent resource back to LIJ to rectify the incomplete survey / displaced machine chain.
2026-02-28 | 2026-02-23 | Richard Perez | LIJ | Same room / anesthesia station area | LIJ-2026-02-21-RETURN-01 |  | Rectification Visit | Revisit / Remediation | 1 |  |  |  |  | 1.2 | 1.3 | 0.25 | [5 empty] | Rework | WNH270OPR403 | LIJ-MACH-D | User-provided tracker screenshot + chat context | Subsequent visit found same room with a different anesthesia workstation present; spare present on the later visit.
2026-02-28 | 2026-02-23 | Richard Perez | LIJ | Same room / anesthesia station area | LIJ-2026-02-21-RETURN-01 |  | Survey Completion / Recheck | Survey / Validation | 1 |  |  |  |  | 1.15 | 1.25 | 0 | [5 empty] | Throughput | WNH270OPR403 | LIJ-MACH-D | User-provided tracker screenshot + chat context | Survey / validation work resumed after the return touch; tie to same case rather than counting as a clean new deployment.
2026-03-19 | 2026-03-16 | Richard Perez | NSUH | Shipment / 1 Marcus relay | NSUH-2026-03-19-SHIP-01 |  | Shipment Reminder / Coordination | Logistics | 1 |  |  |  |  | 1 | 1.05 | 0 | [5 empty] | Logistics |  |  | Teams screenshot from user | Friendly reminder that NSUH was expecting a shipment that day: Cybernets, Neurons, and Neuron Power Cables.
2026-03-19 | 2026-03-16 | Richard Perez | NSUH | Shipment / 1 Marcus relay | NSUH-2026-03-19-SHIP-01 |  | Return Dispatch / Logistics Move | Logistics | 3 |  |  |  |  | 1 | 1.1 | 0.5 | [5 empty] | Logistics |  | 3 pallets / 1 Marcus to NSUH | Teams screenshot from user | Confirmed pickup / relay from 1 Marcus to NSUH; thread mentions 3 pallets being loaded for delivery.
2026-03-30 | 2026-03-30 | Geoff Gerber | 1 Marcus -> NSUH |  |  | NSUH Incident Response | Root Cause Investigation | Troubleshooting / Incident Response | 2 | Events | L | 7 | 0.5 | 1.1 | 1.15 | 0 |  |  |  | Yes | NSUH-Specific Requirements |  |  | Week of 3-30 tracker | Re-imaged 2 Cybernets to validate COM port failure theory prior to redeploy
2026-03-31 | 2026-03-30 | Geoff Gerber | 1 Marcus |  |  | Incident Response & Troubleshooting | Re-Imaging / Rework | Revisit / Remediation | 1 | Events | XL | 2.75 | 0.75 | 1.15 | 1.2 | 0 |  |  |  | Review | Incident Carryover |  |  | Week of 3-30 tracker | Bulk remediation of Cybernets following confirmed COM port issue
2026-04-01 | 2026-03-30 | Geoff Gerber | 1 Marcus |  |  | Logistics & Material Flow | Inventory Reconciliation | Inventory / Staging / Cleanup | 1 | Events | M | 1.25 | 0.25 | 1 | 1 | 0 |  |  |  | Yes | Stock-Constrained Execution |  |  | Week of 3-30 tracker | Inventory management to restore accurate stock counts and deployment readiness
2026-04-02 | 2026-03-30 | Geoff Gerber | NSUH |  |  | Logistics & Material Flow | Shipment / Delivery Coordination | Logistics | 1 | Events | L | 1.75 | 0.5 | 1 | 1.05 | 0 |  |  |  | Yes | Multi-Site Pivot |  |  | Week of 3-30 tracker | Delivered re-imaged Cybernets and coordinated field handoff
2026-04-02 | 2026-03-30 | Geoff Gerber | NSUH |  |  | Reporting & Documentation | Tooling / Prep | Reporting / Documentation | 1 | Events | M | 1 | 0.25 | 1 | 1 | 0 |  |  |  | Yes | Incident Carryover |  |  | Week of 3-30 tracker | Updated shared driver repositories to support upcoming incident responses
2026-04-03 | 2026-03-30 | Geoff Gerber | NSUH |  |  | Incident Response & Troubleshooting | Production Remediation | Troubleshooting / Incident Response | 1 | Events | L | 7 | 0.5 | 1.1 | 1.15 | 0 |  |  |  | Yes | Post-Deployment Remediation |  |  | Week of 3-30 tracker | Installed validated drivers on affected deployed Cybernets
2026-04-04 | 2026-03-30 | Geoff Gerber | NSUH |  |  | Deployment Execution | Deployment Coverage | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Weekend / After-Hours Coverage |  |  | Attendance Bridge + Week of 3-30 | Weekend deployment coverage
2026-04-05 | 2026-03-30 | Geoff Gerber | NSUH |  |  | Logistics & Material Flow | Cleanup | Inventory / Staging / Cleanup | 1 | Events | M | 1.25 | 0.25 | 1 | 1 | 0 |  |  |  | Yes | Post-Deployment Remediation |  |  | Week of 3-30 tracker | Post-deployment cleanup and workspace reset
2026-03-30 | 2026-03-30 | Alejandro Perales | NSUH |  |  | Training & Knowledge Transfer | Training / Coaching | Training / Enablement | 1 | Events | M | 0.75 | 0.25 | 1 | 1 | 0 |  |  |  | Yes | NSUH-Specific Requirements |  |  | Week of 3-30 tracker | Provided hands-on SIS installation and troubleshooting training to Julio and Christopher
2026-03-30 | 2026-03-30 | Alejandro Perales | NSUH |  |  | Configuration & Build Operations | Configuration Validation | Configuration / Build | 1 | Events | M | 3 | 0.25 | 1 | 1 | 0 |  |  |  | Yes | Throughput |  |  | Week of 3-30 tracker | Validated and prepared additional Cybernets to meet daily deployment quota
2026-03-31 | 2026-03-30 | Alejandro Perales | NSUH |  |  | Incident Response & Troubleshooting | Production Remediation | Troubleshooting / Incident Response | 1 | Events | L | 7 | 0.5 | 1.1 | 1.15 | 0 |  |  |  | Yes | Post-Deployment Remediation |  |  | Week of 3-30 tracker | Troubleshot SIS Offline Viewer issues and confirmed reliable vitals streaming
2026-03-31 | 2026-03-30 | Alejandro Perales | NSUH |  |  | Deployment Execution | Survey / Validation | Survey / Validation | 1 | Events | M | 1.25 | 0.25 | 1.05 | 3 | 0 |  |  |  | Yes | Client Deliverable |  |  | Week of 3-30 tracker | Completed EPIC TDR validation and OR device surveys
2026-04-01 | 2026-03-30 | Alejandro Perales | NSUH |  |  | Configuration & Build Operations | Configuration / Build | Configuration / Build | 1 | Events | M | 3 | 0.25 | 1 | 1 | 0 |  |  |  | Yes | Throughput |  |  | Week of 3-30 tracker | QA and final prep of Cybernets to close deployment gap
2026-04-02 | 2026-03-30 | Alejandro Perales | NSUH |  |  | Incident Response & Troubleshooting | Live Issue Triage | Troubleshooting / Incident Response | 1 | Events | L | 7 | 0.5 | 1.1 | 1.15 | 0 |  |  |  | Yes | Incident Carryover |  |  | Week of 3-30 tracker | Handled SIS-related incidents during active deployment window
2026-04-03 | 2026-03-30 | Alejandro Perales | NSUH |  |  | Logistics & Material Flow | Cleanup | Logistics | 1 | Events | L | 1.75 | 0.5 | 1 | 1.05 | 0 |  |  |  | Yes | Post-Deployment Remediation |  |  | Week of 3-30 tracker | Facilitated disposal coordination and removal of deployment packaging
2026-04-04 | 2026-03-30 | Alejandro Perales | NSUH |  |  | Deployment Execution | Deployment Coverage | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Weekend / After-Hours Coverage |  |  | Attendance Bridge + Week of 3-30 | Weekend deployment coverage across multiple ORs
2026-03-30 | 2026-03-30 | Khadejah Harrison | 1 Marcus |  |  | Logistics & Material Flow | Inventory Reconciliation | Inventory / Staging / Cleanup | 1 | Events | M | 1.25 | 0.25 | 1 | 1 | 0 |  |  |  | Yes | Stock-Constrained Execution |  |  | Week of 3-30 tracker | Sorted and categorized deployment stock from NHP and surrounding sites to restore usable workflow
2026-03-31 | 2026-03-30 | Khadejah Harrison | 1 Marcus |  |  | Logistics & Material Flow | Inventory Reconciliation | Inventory / Staging / Cleanup | 1 | Events | M | 1.25 | 0.25 | 1 | 1 | 0 |  |  |  | Yes | Workflow Recovery |  |  | Week of 3-30 tracker | Further refined equipment grouping and staging to support troubleshooting and redeployment
2026-04-01 | 2026-03-30 | Khadejah Harrison | 1 Marcus |  |  | Workflow Governance & Process Control | Process Correction / Standardization | Management / Operational Control | 1 | Events | M | 1 | 0.25 | 1 | 1 | 0 |  |  |  | No | Process Control |  |  | Week of 3-30 tracker | Maintained organized floor layout and labeled areas to stabilize configuration and remediation flow
2026-04-03 | 2026-03-30 | Khadejah Harrison | 1 Marcus |  |  | Workflow Governance & Process Control | Process Correction / Standardization | Management / Operational Control | 1 | Events | M | 1 | 0.25 | 1 | 1 | 0 |  |  |  | No | Process Control |  |  | Week of 3-30 tracker | Sustained floor control and equipment consolidation during ongoing incident remediation
2026-03-30 | 2026-03-30 | Emmanuel Sanchez | NSUH |  |  | Deployment Execution | Deployment Coverage | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Attendance-Based Allocation |  |  | Attendance Bridge | Fallback assignment based on recorded attendance; no specific narrative logged
2026-03-31 | 2026-03-30 | Emmanuel Sanchez | NSUH |  |  | Deployment Execution | Deployment Coverage | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Attendance-Based Allocation |  |  | Attendance Bridge | Fallback assignment based on recorded attendance; no specific narrative logged
2026-04-02 | 2026-03-30 | Emmanuel Sanchez | NSUH |  |  | Deployment Execution | Deployment Coverage | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Attendance-Based Allocation |  |  | Attendance Bridge | Fallback assignment based on recorded attendance; no specific narrative logged
2026-04-04 | 2026-03-30 | Emmanuel Sanchez | NSUH |  |  | Deployment Execution | Deployment Coverage | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Weekend / After-Hours Coverage |  |  | Attendance Bridge | Fallback weekend coverage based on attendance; narrative not separately recorded
2026-03-30 | 2026-03-30 | Valentyn Nykoliuk | 1 Marcus |  |  | Configuration & Build Operations | Configuration Push | Configuration / Build | 1 | Events | M | 3 | 0.25 | 1 | 1 | 0 |  |  |  | Yes | Throughput |  |  | Week of 3-30 tracker | Configured Cybernets destined for NSUH; verified processes prior to shipping
2026-03-31 | 2026-03-30 | Valentyn Nykoliuk | 1 Marcus |  |  | Configuration & Build Operations | Configuration Push | Configuration / Build | 1 | Events | M | 3 | 0.25 | 1 | 1 | 0 |  |  |  | Yes | Throughput |  |  | Week of 3-30 tracker | Continued Cybernet configuration with updated procedure including SIS Offline Viewer
2026-04-01 | 2026-03-30 | Valentyn Nykoliuk | 1 Marcus |  |  | Configuration & Build Operations | Configuration Push | Configuration / Build | 1 | Events | M | 3 | 0.25 | 1 | 1 | 0 |  |  |  | Yes | NSUH-Specific Requirements |  |  | Week of 3-30 tracker | Final bench configuration pass prior to field deployment
2026-04-02 | 2026-03-30 | Valentyn Nykoliuk | NSUH |  |  | Deployment Execution | Field Deployment | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Field Execution |  |  | Week of 3-30 tracker | Deployed Cybernets at NSUH; renamed systems and verified COM port assignments
2026-03-30 | 2026-03-30 | Asher Ali | NSUH |  |  | Deployment Execution | Deployment Coverage | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Attendance-Based Allocation |  |  | Attendance Bridge | Fallback assignment based on recorded attendance; no specific narrative logged
2026-03-31 | 2026-03-30 | Asher Ali | NSUH |  |  | Deployment Execution | Deployment Coverage | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Attendance-Based Allocation |  |  | Attendance Bridge | Fallback assignment based on recorded attendance; no specific narrative logged
2026-04-01 | 2026-03-30 | Asher Ali | NSUH |  |  | Deployment Execution | Deployment Coverage | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Attendance-Based Allocation |  |  | Attendance Bridge | Fallback assignment based on recorded attendance; no specific narrative logged
2026-04-04 | 2026-03-30 | Asher Ali | NSUH |  |  | Deployment Execution | Deployment Coverage | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Weekend / After-Hours Coverage |  |  | Attendance Bridge | Fallback weekend coverage based on attendance; narrative not separately recorded
2026-03-31 | 2026-03-30 | Patricia Marrero | NSUH |  |  | Deployment Execution | Deployment Coverage | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Attendance-Based Allocation |  |  | Attendance Bridge | Fallback assignment based on recorded attendance; no specific narrative logged
2026-04-02 | 2026-03-30 | Patricia Marrero | NSUH |  |  | Deployment Execution | Deployment Coverage | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Attendance-Based Allocation |  |  | Attendance Bridge | Fallback assignment based on recorded attendance; no specific narrative logged
2026-04-04 | 2026-03-30 | Patricia Marrero | NSUH |  |  | Deployment Execution | Deployment Coverage | Deployment / Field Support | 1 | Events | L | 1.5 | 0.5 | 1 | 1 | 0 |  |  |  | Yes | Weekend / After-Hours Coverage |  |  | Attendance Bridge | Fallback weekend coverage based on attendance; narrative not separately recorded
2026-04-06 | 2026-04-06 | Rich Perez | 1 Marcus | Suite 1 | Josh KPI Report / Client Correspondence / Managing Team Split | [8 empty] | 3 | 1 | 0
2026-04-07 | 2026-04-06 | Rich Perez | NSUH | Schwartz | Bonita KPI Report / Go one by one through cells of my task tracker to populate her template / Logistical Support | [8 empty] | 2 | 1 | 0
2026-04-08 | 2026-04-06 | Rich Perez | LIJ | CCMC | Bonita KPI Report / Invoice / Billing / Survey for roaming spare | [8 empty] | 2 | 1 | 0
2026-04-09 | 2026-04-06 | Rich Perez | 1 Marcus | NSUH | Val Task Tracking Confirmation / Staffing / Configurations | [8 empty] | 3 | 1 | 0
2026-04-10 | 2026-04-06 | Rich Perez | 1 Marcus | 1 Marcus | Inventory / Invoicing / Client Correspondence / Logistical Support | [8 empty] | 1 | 1 | 0
2026-04-11 | 2026-04-06 | Rich Perez | 1 Marcus | NSUH | [9 empty] | 1 | 1 | 0
[14 empty] | 1 | 1 | 0
[14 empty] | 1 | 1 | 0
Formulas:
Week Start = [Event Date]-WEEKDAY([Event Date],2)+1
Week Start = IF([Event Date]="","",[Event Date]-WEEKDAY([Event Date],2)+1)

## Daily Narrative Log
OR Cybernet and Neuron Task Tracker ¦ Daily Narrative Log
This is the detail sheet: date, site, workstream, and narrative context for each person/day.
Manager note: include pivots, training, meetings, and rework. Those hours are project work, not noise.
Date | Day | Person | Site | Primary Workstream | Method / Detail | Record State
2026-03-12 | Thursday | Richard Perez | Pre-week planning / logistics / controls | Invites, attendance, logistics, documentation | Sent out invites for night configurations, completed logistics with Tim for NSUH PSP and confirmed Friday morning's second shipment of peripherals, shared attendance views with Bonita, pushed attendance tracker updates, and created ticket-submission documentation to support the next deployment cycle. | Recorded
2026-03-13 | Friday | Geoff Gerber | PSP ICU / staging | Preparation, QA, staging | Unpacked equipment to remove cardboard, QA'd Cybernets, staged 2 peripheral sets for that weekend's deployments, and pivoted remaining equipment staging into PSP ICU offices to stay compliant with hospital no-cardboard policy. | Recorded
2026-03-13 | Friday | Richard Perez | Staging / prep area | Equipment prep / unboxing | Worked with Asher and Emmanuel to unbox all equipment for the upcoming weekend under the no-cardboard requirement after earlier Friday prep activity. | Recorded
2026-03-13 | Friday | Asher Ali | Staging / prep area | Equipment prep / unboxing | Worked with Richard and Emmanuel to unbox all equipment for the upcoming weekend under the no-cardboard requirement after earlier Friday prep activity. | Recorded
2026-03-13 | Friday | Emmanuel Sanchez | Staging / prep area | Equipment prep / unboxing | Worked with Richard and Asher to unbox all equipment for the upcoming weekend under the no-cardboard requirement after earlier Friday prep activity. | Recorded
2026-03-14 | Saturday | Richard Perez | NSUH Main ORs 1-18 (excluding 13) | PM / logistics / troubleshooting / documentation / client coordination | Managed team flow, issue handling, tickets, client coordination, survey capture, and technical follow-up across the deployment window. | Recorded
2026-03-14 | Saturday | Alejandro Perales | NSUH Main ORs | Configuration / troubleshooting / SIS workaround | Drove configuration and remediation work, including the new SIS workaround and standardization effort across the OR environment. | Recorded
2026-03-14 | Saturday | Emmanuel Sanchez | NSUH Main ORs | Configuration / troubleshooting | Supported Cybernets configuration, troubleshooting, and consistency work across the active OR push. | Recorded
2026-03-14 | Saturday | Khalida Abdul-Rahman | NSUH Main ORs | Configuration / troubleshooting | Supported live configuration and troubleshooting while helping move the OR workstream toward a cleaner, more repeatable standard. | Recorded
2026-03-14 | Saturday | Valentyn Nykoliuk | NSUH Main ORs | Configuration / troubleshooting | Supported active Cybernets configuration, field remediation, and live issue handling across the main OR workstream. | Recorded
2026-03-14 | Saturday | Asher Ali | NSUH Main ORs | Troubleshooting / staging / workflow support | Supported staging, workflow support, physical prep, and troubleshooting as the team kept the Saturday push moving. | Recorded
2026-03-15 | Sunday | Richard Perez | NSUH PSP | PM / logistics / QA / documentation / training / client response | Managed supplies, logistics, QA, survey and documentation, training, and client-response follow-up to keep the output clean and client-ready. This also included disposal logistics / protocol, survey button-up, ticket submissions based on healthcare-professional reports, physical device surveying per Tim's request, physical disposal handling, and capture of follow-up access / deployment requests for Tim. | Recorded
2026-03-15 | Sunday | Alejandro Perales | NSUH PSP | Windows activation / labeling | Activated Windows and labeled devices to ensure readiness and traceable identification. | Recorded
2026-03-15 | Sunday | Asher Ali | NSUH PSP | Cable management / survey support | Completed cable management and helped complete the survey and closeout record. | Recorded
2026-03-16 | Monday | Richard Perez | NSUH / PSP follow-up | Readiness follow-up / issue handling / reporting | Handled Monday readiness follow-up, documentation, and current requests tied to SIS, Imprivata, survey access, and workflow standardization following the weekend push. | Recorded
2026-03-16 | Monday | Alejandro Perales | Overnight configuration coverage | Configuration / domain-join remediation | Most Cybernet units failed domain join after credential expiration at 1:00 AM; waited for post-install completion, reset units, and re-ran process. Most completed successfully; 1 device still failing after 3 reset attempts. | Recorded
2026-03-16 | Monday | Asher Ali | Overnight configuration coverage | Configuration support | Supported reruns / resets during domain-join remediation event. | Recorded
2026-03-16 | Monday | Emmanuel Sanchez | Overnight configuration coverage | Configuration support | Supported reruns / resets during domain-join remediation event. | Recorded
2026-03-16 | Monday | Geoff Gerber | Configuration staging site (exact site not captured) | Imaging / configuration | Helped configure and image over 10 Cybernets, likely closer to 15, for upcoming deployment readiness. | Recorded
2026-03-17 | Tuesday | Richard Perez | NSUH | Readiness / escalation / procurement support | Submitted SCTASK3874877 for NSUH OR Cybernet baseline review; compared WMH300OPR341 to WMH300PSP024; identified baseline / application-access misalignment with CTX_Prod_TEG_Manager as current top gap; added OU / group comparison findings to work notes; validated cable counts to support Tim's PO planning; created Friday deployment invite coverage; and tracked attendance for the active push. | Recorded
2026-03-17 | Tuesday | Richard Perez | Cross-team coordination | Directory / access follow-up | Responded to missing computer objects for 33 workstations after security approval on Autologon / OU actions; coordinating desktop follow-up for object creation. | Recorded
2026-03-17 | Tuesday | Alejandro Perales | On-site configuration | OOBE / configuration / application install | Completed OOBE and configuration on all new Cybernet units on-site; installed SIS and NSUH app stack; identified older pallet for follow-up review; set aside WMH300OPT388 for missing stylus; relocated remaining ThinkCentres and secured loose equipment. | Recorded
2026-03-17 | Tuesday | Asher Ali | On-site configuration | Configuration support / floor organization | Remained on-site with Alejandro through OOBE / configuration completion and related equipment organization. | Recorded
2026-03-17 | Tuesday | Geoff Gerber | One Marcus | Inventory / procurement support | Helped ascertain cable counts tied to NSUH-related inventory and procurement planning. | Recorded
2026-03-18 | Wednesday | Richard Perez | 1 Marcus + 300 Community Drive / NSUH (+ possible HQ) | Incident response / access escalation / workflow anchoring | Led multi-site incident response after an issue first tracked as SIS not streaming vitals was narrowed into an account / Citrix access problem in the NSUH environment. Citrix had been tested and loading at deployment and afterward; the current issue surfaced after desktop-support account refresh activity aligned to prior ticket specs. Coordinated invites and attached the necessary parties, covered 1 Marcus and 300 Community Drive / NSUH by EoD, handled inventory / missing-computer-object follow-up, corresponded with Northwell account control, and pivoted Patricia from One Marcus to NSUH to relay Geoff's laptop for file-share support used in Cybernet configuration. Pushed the working next-step view that security / access teams may need to validate permissible groups and permissions spanning Imprivata, AutoLogon, Citrix, and SIS. The day also involved repeated meetings, training, and pivots to Tim's demands while anchoring the workflow. | Recorded
2026-03-18 | Wednesday | Geoff Gerber | NSUH | Post-deployment issue rectification / inventory support | Provided post-deployment issue rectification and support and ensured accurate inventory counts. | Recorded
2026-03-18 | Wednesday | Valentyn Nykoliuk | One Marcus | Configuration push | Pushing configurations at 1 Marcus for the current workstream. | In Progress
2026-03-18 | Wednesday | Patricia Marrero | One Marcus -> NSUH | Incident-response logistics / file-share support | Relayed Geoff's laptop from One Marcus to NSUH to support current incident response. The laptop is one of the computers used for file shares that facilitate Cybernet configurations. | Recorded
2026-03-18 | Wednesday | Emmanuel Sanchez | NSUH / support coverage | Configuration / incident support | Invoked for current support coverage. | Assigned
2026-03-18 | Wednesday | Asher Ali | NSUH / support coverage | Configuration / incident support | Invoked for current support coverage. | Assigned
2026-03-18 | Wednesday | Khadejah Harrison | One Marcus / workflow control | Configuration push / process correction / cable logistics | Pushed configurations while clarifying that the control being disabled was the sleep / black-screen behavior rather than a pure screensaver setting, helping reduce repeat confusion during troubleshooting. Also told Geoff additional power cables were not needed because local supply was already available. | Recorded
2026-03-18 | Wednesday | Geoff Gerber | NSUH incident-response meeting / imaging workflow | Imaging clarification / scope defense | Clarified during incident-response discussion that he completed most of the images and that the team is using the exact server-based image set, helping rebut claims that the current Citrix issue stemmed from ad hoc CDW imaging misconfiguration. The comparative note that LIJ devices do not show the same Citrix behavior supports the working view that this is more likely NSUH-specific than a broad imaging defect. | Recorded
2026-03-19 | Thursday | Geoff Gerber | One Marcus -> NSUH | Stock collection / shipment coordination | Collected all stock at 1 Marcus, met the shipment at NSUH, and coordinated the stock that needs to be unpacked / unboxed tomorrow. | Recorded
2026-03-19 | Thursday | Richard Perez | Multi-site / night-push coverage | PM coordination / meetings / training / configuration push | Balanced meetings, training, and pivots to Tim's demands while coordinating the overnight Neuron and Cybernet configuration push to meet deadline / quota. This phase also reflects the team's ongoing work to learn NSUH-specific conventions and first-time requirements; a recent example is learning to install a needed feature as a service to pass SIS streaming. Geoff handled stock collection / shipment coordination feeding the next unpack / unbox wave; tonight's configuration support crew includes Khadejah, Alejandro, and Asher. After hours, also tightened Neuron tracker controls so device / MAC visibility stayed readable during the push. | Recorded
2026-03-19 | Thursday | Alejandro Perales | One Marcus / configuration floor | Validation / configuration / Imprivata follow-up | Assisted with validation and configuration of Cybernets returned from NSUH and began working through a pallet of previously imaged / unknown Cybernet units with irregular labeling. AutoLogon was not functioning on those units, so resets were performed before proceeding through the standard workflow by hostname list. Hostnames 394 and 395 could not be located in One Marcus, so work proceeded with 396 to maintain progress. Fully configured 6 Cybernets (OOBE, SIS, and required applications completed) with 2 additional units in post-installation on the floor. Also flagged Imprivata issues on Cybernets 367, 368, and 369 in the conference room, where devices still showed the system-tray icon but no longer triggered the expected lock screen on restart. Moved 2-3 AIO ThinkCentres to the main floor, secured the hand scanner and labeler, and noted the need for labeling plus follow-up on the remaining 6 units on the pallet. | Recorded
2026-03-19 | Thursday | Asher Ali | One Marcus / returned NSUH units | Imprivata-list validation / CIS install / configuration support | Upon Alejandro's arrival, Asher was validating the Imprivata list for Cybernet devices returned from NSUH and installing CIS on those units. He then continued supporting the overnight configuration push. | Recorded
2026-03-19 | Thursday | Khadejah Harrison | LI SDF -> 1 Marcus / night push | Location handoff / configuration push | Helped push Neuron and Cybernet configurations to meet the deadline / quota while staying aligned on location handoffs, with movement planned from the current site to 1 Marcus for Neuron work once the active task was complete. | Recorded
2026-03-19 | Thursday | Emmanuel Sanchez | One Marcus / returned NSUH units | Imprivata-list validation / CIS install | Upon Alejandro's arrival, Emmanuel was validating the Imprivata list for Cybernet devices returned from NSUH and installing CIS on those units at the start of shift while supporting current configuration work. | Recorded
2026-03-20 | Friday | Richard Perez | Prep / transport / delivery coverage | QA / transport / delivery / testing coordination | Continued the pre-deployment cycle with QA, transport & delivery, and additional testing while coordinating the workstream and accounting for environment-specific requirements that were still being uncovered. | Recorded
2026-03-21 | Saturday | Richard Perez | Two deployment sites (specific pair not yet broken out in current note) | PM / multi-site deployment orchestration | Orchestrated two sites on Saturday while managing team flow, live pivots, and deployment readiness as the team continued working through NSUH-specific conventions and newly learned requirements. | Recorded
2026-03-21 | Saturday | Patricia Marrero | Saturday deployment coverage (site not yet separately broken out) | Deployment support | Part of the Saturday deployment team with Richard, Cristian, and Alejandro. Current note does not separately break out her site/task beyond active deployment support. | Recorded
2026-03-21 | Saturday | Alejandro Perales | Saturday deployment coverage (site not yet separately broken out) | Deployment support | Part of the Saturday deployment team with Richard, Patricia, and Cristian. Current note does not separately break out site/task beyond active deployment support. | Recorded
2026-03-21 | Saturday | Cristian | Saturday deployment coverage (site not yet separately broken out) | Deployment support | Part of the Saturday deployment team with Richard, Patricia, and Alejandro. | Recorded
2026-03-22 | Sunday | Richard Perez | Deployment + shipment / disposal coverage | PM / deployment / logistics orchestration | Orchestrated shipment and disposal on Sunday in addition to deployment, keeping field execution and material flow aligned across the day. | Recorded
2026-03-22 | Sunday | Asher Ali | Sunday deployment coverage (site not yet separately broken out) | Deployment support | Part of the Sunday deployment team with Delroy, Alejandro, Geoff, and Chris Cummings. | Recorded
2026-03-22 | Sunday | Delroy | Sunday deployment coverage (site not yet separately broken out) | Deployment support | Part of the Sunday deployment team with Asher, Alejandro, Geoff, and Chris Cummings. | Recorded
2026-03-22 | Sunday | Alejandro Perales | Sunday deployment coverage (site not yet separately broken out) | Deployment support | Part of the Sunday deployment team with Asher, Delroy, Geoff, and Chris Cummings. | Recorded
2026-03-22 | Sunday | Geoff Gerber | Sunday deployment coverage (site not yet separately broken out) | Deployment support | Part of the Sunday deployment team with Asher, Delroy, Alejandro, and Chris Cummings. | Recorded
2026-03-22 | Sunday | Chris Cummings | Sunday deployment coverage (site not yet separately broken out) | Deployment support | Part of the Sunday deployment team with Asher, Delroy, Alejandro, and Geoff. | Recorded
2026-03-23 | Monday | Alejandro Perales | NSUH | Neuron repurposing / configuration | Worked with Asher and Emmanuel to repurpose and configure 22 Neuron devices for NSUH in a single shift. All 22 were labeled with machine name and MAC address, documented in the tracking spreadsheet, and left ready for NSUH use. Identified a separate 'Wave 3 Neurons' pallet and intentionally did not touch it so the designated deployment phase would not be disrupted. Remaining work toward the 45-Neuron target was dependent on additional stock. | Recorded
2026-03-23 | Monday | Asher Ali | NSUH | Neuron repurposing / configuration | Worked collaboratively with Alejandro and Emmanuel to complete 22 Neuron repurposes / configurations for NSUH in one shift, including machine-name / MAC labeling and tracker documentation. | Recorded
2026-03-23 | Monday | Emmanuel Sanchez | NSUH | Neuron repurposing / configuration | Worked collaboratively with Alejandro and Asher to complete 22 Neuron repurposes / configurations for NSUH in one shift, including machine-name / MAC labeling and tracker documentation. | Recorded
2026-03-23 | Monday | Khadejah Harrison | Configuration floor / incident response coordination | Incident response intake / ticket escalation / submissions | Handled return-related issue intake, coordinated ticket escalation and submissions, joined workflow discussions on how to process problem Cybernets, and helped move affected units into the working area so they could be worked through in batches. | Recorded
2026-03-23 | Monday | Valentyn Nykoliuk | 1 Marcus / Configurations | Configuration push / process correction / cable logistics | Configured Cybernets destined for NSUH. Verified all processes were operational before shipping.
2026-03-24 | Tuesday | Alejandro Perales | NSUH | Stock-constrained Neuron configuration / troubleshooting / training | Continued Neuron configuration as available stock allowed. Provided guidance and training to Asher and Emmanuel on troubleshooting the SIS Offline Viewer issue and resolved the issue on Cybernet 348 by uninstalling and reinstalling the application. Remaining progress was blocked by lack of additional stock. | Recorded
2026-03-24 | Tuesday | Asher Ali | NSUH | Configuration support / troubleshooting training | Continued Neuron configuration as stock allowed and received guided troubleshooting training on resolving SIS Offline Viewer issues for future shifts. | Recorded
2026-03-24 | Tuesday | Emmanuel Sanchez | NSUH | Configuration support / troubleshooting training | Continued Neuron configuration as stock allowed and received guided troubleshooting training on resolving SIS Offline Viewer issues for future shifts. | Recorded
2026-03-24 | Tuesday | Geoff Gerber | Configuration floor / NSUH support | Device-status accounting / packaging / readiness control | Documented detailed status for Cybernets 337, 340, 344, 348, 367, 368, 369, 402, 403, 404, and 405. Boxed and palletized 337, 340, and 344 after SIS / VM configuration; boxed and palletized 402 and 403 after full app installs, AutoLogon, VMware, and SIS completion; kept 367-369 plugged in and online awaiting Imprivata push; ran 404 and 405 through OOBE / postinstall as demos with Cyen and marked them ready for apps; and set aside 348 after the SIS Offline Viewer produced no visible action once PA credentials were entered. | Recorded
2026-03-24 | Tuesday | Khadejah Harrison | Configuration floor / incident response coordination | Workflow control / ticket coordination / escalation / submissions | Kept the line aligned through ticket coordination, escalation, and submissions while directing the team to prioritize the Cybernets already in the area for SIS, VMware, and Imprivata validation before starting new imaging, reinforcing a more disciplined troubleshooting flow and reducing repeat questions. | Recorded
2026-03-25 | Wednesday | Geoff Gerber | NSUH + L&D OR C / configuration floor | Counts / handoff reporting / configuration / incident response / SIS install | Wrapped up counts, pushed configurations, tested production, and supported incident response at L&D OR C while installing SIS. Also left a detailed handoff so the night crew knew where the unboxed Cybernets stood: 17 NSUH configured units, 5 NSUH mid-config units, 6 NSUH units with uncertain naming / match status, 1 IR Cybernet, 3 LIJ Cybernets, 3 additional NSUH units noted as uncertain (OPR321, OPR322, OPR330), and 57 unconfigured Wave 2 Cybernets. Within the unboxed set, 367-369 were confirmed as having received Imprivata and were packed on a pallet; 404 and 405 had apps, VMware, and SIS installed/configured and were packed in boxes; 406-408 had run OOBE / postinstall and still needed apps; 409 had run OOBE and was mid-postinstall when he left; and 348 remained set aside due to the Offline Viewer issue. | Recorded
2026-03-26 | Thursday | Geoff Gerber | Configuration floor / server rack | Per-device remediation / file transfer / AutoLogon / SIS / network troubleshooting | Reviewed the 4 Cybernets left on top of the server rack. 415 had apps except SIS and no Imprivata; copying SIS files from the Akbarinator failed because pathing between devices was rejected under PA credentials, so the files were transferred using his own laptop instead. 412 still needs post-install; both LAN ports failed across multiple cables, wall jacks, and both onboard ports, so an image stick may be needed. 416 attempts AutoLogon to the wrong hostname and likely needs the AutoLogon script re-run; it also has no Imprivata. 410 had apps except SIS and no Imprivata; the computer was named 331, so the AutoLogon script needs to be re-run there as well. | Recorded
2026-03-26 | Thursday | Richard Perez | NSUH / deployment follow-up | Incident intake / failed deployment report | Received report from the Metasource team lead that attempted deployment of WMH300OPR384 failed because the unit showed bad COM-port behavior, displaying comms 3, 4, 5, and 6. The device was moved to the bad pile for follow-up and exclusion from active deployment stock. | Recorded
2026-03-23 | Monday | Richard Perez | NSUH / PM coordination | PM continuity / stock-target oversight | Maintained meetings, client coordination, tracker visibility, and stock / target awareness while the team repurposed available Neurons for NSUH and worked against the Wednesday target. | Recorded
2026-03-24 | Tuesday | Richard Perez | NSUH / workflow control | PM continuity / troubleshooting oversight | Maintained workflow control and status visibility during stock-constrained configuration and coordinated around SIS Offline Viewer troubleshooting so the team could continue configuration work with fewer repeated questions. | Recorded
2026-03-25 | Wednesday | Richard Perez | NSUH + PSP / L&D OR C | Counts / configuration push / incident response | Wrapped counts, pushed configurations, supported production testing and incident response at L&D OR C, coordinated around Geoff's SIS install, and provided live status accounting for PSP / NSUH / LIJ / IR Cybernets plus remaining Wave 2 stock so the team had a current readiness picture. | Recorded
2026-03-25 | Wednesday | Alejandro Perales | NSUH / configuration floor | Configuration push / troubleshooting support | Supported the Wednesday configuration run and assisted with troubleshooting on the floor, helping keep device configuration moving while production-readiness and incident-response items were being worked in parallel. | Recorded
2026-03-26 | Thursday | Alejandro Perales | NSUH / configuration floor | Configuration / troubleshooting continuity | Continued configuration work and troubleshooting support on the floor as the team worked through remaining devices and blockers following the Wednesday handoff. | Recorded
2026-03-26 | Thursday | Valentyn Nykoliuk | 1 Marcus / Configurations | Configuration push / process correction / cable logistics | Configured Cybernets destined for NSUH. Completed updated procedure including installing SIS offline viewer along with previous steps.
2026-03-27 | Thursday | Richard Perez | NSUH | Incident Response | COM Ports: - Cybernets rejected in select ORs - Report of defective ports - Incident response discerns that post-install & windows arbitrarily dictate COM port numbers. - CDW resolves to rectify upon return
2026-03-27 | Thursday | Richard Perez | NSUH | Meeting | Buying Cables: - 50 x B1-CFU (Aisys CS2) - COM Ports
2026-03-27 | Thursday | Richard Perez | NSUH | Staffing | Saturday Shift Established Sunday confirmed not to be scheduled according to Tim's DI Schedule / tracker Conversations held and phone calls made throughout the day to solidify coverage
2026-03-27 | Thursday | Richard Perez | 1 Marcus | Reporting
Everyday | Everyday | Alejandro